## Development Governance Matrix
Level | Mandatory Document | Description | AI Governance Assets Required
Portfolio | Enterprise Blueprint | Defines domains, capability areas, capability blocks, modules, ownership boundaries, and target architecture. | Enterprise Architecture Prompt, Capability Taxonomy Rules, Naming Rules
Portfolio | Master Development Plan | Defines development standards, module statuses, execution waves, architecture rules, coding rules, and AI development rules. | Core Development Prompt, Clean Architecture Rules, CQRS Rules, Validation Rules
Portfolio | Blueprint - Master Plan Reconciliation Matrix | Maps Blueprint domains/modules to Master Plan implementation modules, priorities, dependencies, and execution ownership. | Mapping Rules, Dependency Rules, Traceability Rules
Portfolio | AI Prompt & Skill Governance Registry | Defines approved system prompts, master prompts, review prompts, skill packs, rule packs, and validation prompts. | Prompt Governance Rules, Skill Pack Registry, AI Output Validation Rules
Block | Capability Block Documentation | Defines the block scope, purpose, included modules, architecture boundaries, business value, ownership, and governance rules. | Capability Block Prompt, Boundary Rules, Capability Modeling Rules
Block | Capability Block Execution Plan | Defines module sequencing, parallel workstreams, delivery phases, milestones, blockers, and rollout approach. | Execution Planning Prompt, Sequencing Rules, Parallelization Rules
Block | Capability Block Dependency & Integration Map | Defines module dependencies, APIs, events, shared services, infrastructure dependencies, and external integrations. | Dependency Analysis Skill, API/Event Rules, Integration Rules
Block | Capability Block Acceptance & Risk Register | Defines block-level readiness criteria, risks, blockers, compliance risks, integration risks, and release conditions. | Risk Analysis Prompt, Block Acceptance Rules
Module | Module Specification | Defines module scope, objectives, business logic, domain boundaries, lifecycle states, permissions, integrations, and exclusions. | Module System Prompt, Domain Modeling Rules, Business Logic Rules
Module | Module Development Plan | Defines step-by-step implementation order for backend, frontend, persistence, integration, testing, migration, and deployment. | AI Development Workflow Prompt, Backend Rules, Frontend Rules, Migration Rules
Module | Module API / UI / Data / Integration Specification | Defines endpoints, request/response models, UI screens, database design, events, DTOs, validations, localization, and persistence rules. | API Design Rules, UI Rules, Database Rules, Event Contract Rules
Module | Module Security & Permission Matrix | Defines roles, permissions, actor types, RBAC/ABAC rules, entitlement checks, tenant isolation, and restricted actions. | Security Rules, Permission Matrix Prompt, Tenant Isolation Rules
Module | Module Test Plan & Definition of Done | Defines test coverage, acceptance criteria, gateway smoke tests, browser smoke tests, security checks, and completion criteria. | QA Prompt, Testing Rules, Smoke Test Rules, DoD Rules
Delivery | Work Package Checklist | Tracks concrete execution tasks, coding, validation, review, documentation, localization, testing, and completion status. | Delivery Checklist Rules, Completion Validation Rules
Delivery | Code Review Checklist | Verifies architecture compliance, naming, CQRS, DDD, security, tenancy, audit, localization, and test coverage. | Code Review Prompt, Quality Gate Rules
Delivery | QA / Acceptance Report | Records test evidence, acceptance status, defects, unresolved risks, production readiness, and approval decision. | QA Review Prompt, Acceptance Rules, Audit Rules
Delivery | Deployment Checklist & Release Notes | Confirms environment readiness, secrets, gateway routes, migrations, smoke tests, rollback, delivered scope, and known limitations. | Deployment Rules, Release Notes Prompt, Rollback Rules

## PVG
PVG Capability Block — Readiness-Adjusted Development Sequence
Updated from the 2026-08-03 platform readiness audit. The sequence count is unchanged. Seq. 1 is now a mandatory remediation gate: RBAC, audit, workflow and controlled-document capabilities can be reused after hardening, while masking, evidence linking, canonical IDs, metric registry and lakehouse capabilities require implementation or boundary repair before a production PV release.
Foundation gate | BLOCKED | Reusable after hardening | 4 | Missing / rebuild capabilities | 5 | Urgent target | MOD-0234 | Evidence basis | Static repo audit | No runtime PASS
Seq. | Stage / Wave | Module | Module / Capability | Required development scope | Dependency / completion gate | Delivery role | Current code-reality status | PV readiness / recommendation | Required action before gate | Plan impact
1 | Urgent foundation remediation — W-3A0 | MOD-0004, MOD-0018, MOD-0019, MOD-0021, MOD-0023, MOD-0028, MOD-0031, MOD-0040, MOD-0063 | Shared PV Foundation and Safety Case SoR Gate | Establish the minimum production foundation for PV: governed metrics, PV permissions/data scope, patient and reporter masking, audit, workflow, controlled documents, evidence links, canonical/external identifiers, correlation, analytical datasets and the approved native Safety Case ownership model. | Gate closes only when: MOD-0040 identity conflict is resolved; MOD-0019 masking is runtime-proven; MOD-0031 evidence linking is implemented; minimum MOD-0004 and MOD-0063 contracts are operational; MOD-0018/0021/0023/0028 hardening and authenticated smokes pass; MOD-0028 FU06 startup blocker is closed. | Mandatory platform, privacy and ownership foundation | MIXED / NOT RELEASE-READY. Reusable after hardening: MOD-0018, MOD-0021, MOD-0023, MOD-0028. Missing or boundary-blocked: MOD-0004, MOD-0019, MOD-0031, MOD-0040, MOD-0063. | BLOCKED. Apply HARDEN_BEFORE_USE to MOD-0018/0021/0023/0028; IMPLEMENT/COMPLETE foundation for MOD-0019/0031; REBUILD MOD-0040 boundary; do not use MOD-0004/0063 yet. | Run as parallel foundation lanes inside Seq. 1: P0 masking; canonical-ID boundary correction; evidence-linking MVP; metric and analytical-contract MVP; hardening/runtime proof for reusable modules. | Seq. 2–5 may proceed with contract/spec work, but no production PV golden flow can be accepted until this gate is closed.
2 | Urgent — W-3A | MOD-0230 | Case Intake & Triage | Implement minimum valid-case checks, reporter/event/product capture, duplicate screening, triage, routing, assignment, SLA monitoring, follow-up initiation and controlled evidence intake. | Requires Seq. 1 privacy, audit, workflow, evidence and identifier contracts. Stable case, reporter, event and product identifiers are mandatory. | Safety-data entry foundation | PV module code reality was not assessed by the supplied platform-foundation reports. | PLAN-READY / RUNTIME-BLOCKED BY SEQ. 1. | Prepare approved module pack and vertical-slice contracts. Bind permissions to MOD-0018, masking to MOD-0019, audit to MOD-0021, workflow to MOD-0023 and evidence to MOD-0031. | Development can begin after contract freeze; production testing waits for Seq. 1 stop-ship items.
3 | Urgent — W-3B | MOD-0231 | Case Processing — Signal Minimum Scope | Deliver seriousness, expectedness, listedness, causality, outcome, exposure, patient factors, narrative, follow-up status and case lifecycle data required for signal evaluation. | Requires MOD-0230 plus server-side masking, audit, evidence and concurrency controls. Minimum completeness, freshness and data-quality thresholds must pass before MOD-0234 activation. | Signal assessment foundation | PV module code reality was not assessed by the supplied platform-foundation reports. | PLAN-READY / RUNTIME-BLOCKED BY SEQ. 1–2. | Implement only the signal-minimum vertical slice first; preserve extension points for the complete ICSR lifecycle in Seq. 6. | Retain sequence. Do not expand to full ICSR processing before the urgent signal dataset is stable.
4 | Urgent — W-3C | MOD-0232 | MedDRA Coding | Implement MedDRA dictionary/version binding, event and indication coding, coding review, recoding, SMQ support, coding history and audit export. | Requires MOD-0231 case/event records. Each assignment must retain case ID, coded term, MedDRA version, actor, UTC timestamp and audit correlation ID. | Signal terminology foundation | PV module code reality was not assessed by the supplied platform-foundation reports. | PLAN-READY / RUNTIME-BLOCKED BY SEQ. 1–3. | Define governed terminology import/version contracts and coding audit events before UI development. Do not embed dictionary ownership inside MOD-0232 without an approved source contract. | Retain sequence; coding contract can be developed in parallel with late MOD-0231 work.
5 | Urgent — W-3D | MOD-0234 | Signal Management | Implement potential-signal registration, source linkage, validation, prioritisation, evaluation, review-committee decisions, action plans, evidence, due dates, metrics, monitoring, closure and controlled reopening. | Master dependencies MOD-0004 and MOD-0063 are currently unavailable. Production release also requires MOD-0019 masking, MOD-0031 evidence linking, corrected MOD-0040 canonical IDs and a qualified MOD-0230–0232 source feed. | Urgent target capability | RUNTIME-BLOCKED by unavailable metric/lakehouse foundations and unresolved privacy/evidence/identifier capabilities. | DO NOT START AS A SHELL. Specification, object model, workflow and interface contracts can proceed; runtime implementation must use approved minimum MOD-0004/MOD-0063 data products. | Define a thin, production-grade Signal MVP contract within MOD-0004 and MOD-0063; complete P0 privacy and evidence controls; then execute the MOD-0234 vertical slice. | Urgent target remains unchanged, but its go-live date is controlled by Seq. 1 rather than by MOD-0230–0232 alone.
6 | Next stage — W-4A | MOD-0231, MOD-0244, MOD-0258 | Full Case Processing and Conditional Source Integrations | Extend MOD-0231 into the complete ICSR lifecycle. Add Clinical SAE linkage and Argus/ArisG integration only where an approved operating model requires them. | Begin after MOD-0234 stabilises. MOD-0244 requires corrected MOD-0040 and integration reconciliation. MOD-0258 must not create a second authoritative Safety Case record. | Complete case processing and optional source integration | Target-module readiness was not assessed. MOD-0040 dependency is currently boundary-blocked. | NEXT-STAGE / DEPENDENCY-RISK. | Audit MOD-0244/MOD-0258 code reality before committing scope. Resolve SoR and migration/coexistence rules first. | Conditional integrations remain deferred; no impact on the native urgent path.
7A | Next stage — W-4B | MOD-0233, MOD-0022, MOD-0030 | Reporting, Submissions and Regulatory Controls | Implement reportability assessment, schedules, E2B-compatible packages, validation, signatures, amendments, retransmission, acknowledgements, immutable submission records and retention controls. | Requires full MOD-0231 and MOD-0232. MOD-0022 and MOD-0030 were not included in the supplied readiness audit and require separate runtime verification. | Regulatory case-reporting output | NOT ASSESSED in the supplied platform-readiness reports. | SEPARATE READINESS AUDIT REQUIRED. | Inspect e-signature, records-management and submission dependencies before module-pack approval. | Retain next-stage position; readiness must not be inferred from module existence.
7B | Next stage — W-4B, parallel | MOD-0272 | Regulatory Gateway Integration | Implement FDA/EMA/PMDA profiles, secure transport, acknowledgements, rejection handling, retries, monitoring and submission reconciliation. | Develop in parallel with Seq. 7A. Provider certification, acknowledgement processing and reconciliation must pass before electronic submission go-live. | Regulatory transport boundary | NOT ASSESSED in the supplied platform-readiness reports. | SEPARATE READINESS AUDIT REQUIRED. | Confirm whether MOD-0272 is an external-provider register only or includes an implemented adapter/runtime boundary. | Retain parallel sequence; block production submission until provider-specific evidence exists.
8 | Next stage — W-4C | MOD-0235, MOD-0229, MOD-0208 | PV Quality, Audit Packs and CAPA Linkage | Implement case/signal quality reviews, sampling, compliance monitoring, overdue controls, inspection packs, findings, CAPA initiation, due dates and effectiveness checks. | Requires production-proven audit/workflow/document foundations. MOD-0229 and MOD-0208 readiness were not included in the supplied audit. | PV quality and inspection control | PARTIAL FOUNDATION SUPPORT: MOD-0021, MOD-0023 and MOD-0028 are reusable only after hardening; target modules not assessed. | NEXT-STAGE / HARDEN FOUNDATIONS FIRST. | Close audit tamper-evidence/runtime smoke, workflow golden-flow smoke and MOD-0028 FU06 startup blocker. Then audit MOD-0229 and MOD-0208. | Retain sequence; closed-loop quality cannot be claimed until CAPA and audit-pack flows are runtime-proven.
9 | Next stage — W-5A | Canonical FU/module required | Aggregate Safety Reporting | Implement PSUR/PBRER and applicable DSUR schedules, data-lock points, case/exposure aggregation, benefit-risk evaluation, authoring, review, approval and submission. | Requires complete MOD-0231–MOD-0234 data and a production analytical foundation. | Aggregate benefit-risk reporting | No canonical module identity and no code-readiness evidence in supplied reports. | GOVERNANCE-GATED. | Approve existing-module fit versus FU/child versus new canonical module; then perform code-reality assessment. | Planning only; exclude from committed delivery baseline until identity and SoR are approved.
10 | Next stage — W-5B | Canonical FU/module required | PV Governance, PSMF and QPPV Oversight | Govern QPPV/delegates, PV organisation, system inventory, PSMF sections and annexes, procedural controls, changes and compliance oversight. | Requires MOD-0235 plus controlled documents, records management, audit and organisation/person reference data. | PV system governance | No canonical module identity and no code-readiness evidence in supplied reports. | GOVERNANCE-GATED. | Approve SoR and canonical identity. Reuse MOD-0028 only after FU06/runtime hardening; do not use embedded document references as a substitute for MOD-0031. | Planning only until governance decision.
11 | Next stage — W-5C | Canonical FU/module required | Risk Management Plans | Manage identified and potential risks, missing information, RMP versions, pharmacovigilance activities, commitments, reviews and approvals. | Requires confirmed MOD-0234 decisions and regulatory/labeling integration. | Safety-risk governance | No canonical module identity and no code-readiness evidence in supplied reports. | GOVERNANCE-GATED. | Approve independent SoR or FU placement before specification approval. | Planning only until governance decision.
12 | Next stage — W-5D | Canonical FU/module required | Risk-Minimisation Measures | Manage routine and additional measures, controlled materials, implementation plans, distribution, target populations and effectiveness evaluation. | Requires approved RMPs, evidence, metrics, labeling and change-control interfaces. | Risk-control execution | No canonical module identity and no code-readiness evidence in supplied reports. | GOVERNANCE-GATED. | Approve ownership and interfaces; metric and evidence foundations must be operational. | Planning only until governance decision.
13 | Next stage — W-5E | Canonical FU/module required | Literature Surveillance | Implement search strategies, schedules, source ingestion, screening, assessment, duplicate checks, exclusions, case creation and compliance metrics. | Requires MOD-0230, product references, controlled evidence/document services and MedDRA coding. | External safety-source surveillance | No canonical module identity and no code-readiness evidence in supplied reports. | GOVERNANCE-GATED. | Evaluate MOD-0230 FU placement and define document/evidence contracts after MOD-0031 is operational. | Planning only until governance decision.
14 | Next stage — W-5F | Canonical FU/module required | Partner and Affiliate Safety Exchange | Govern safety-data agreements, partner profiles, timelines, inbound/outbound exchange, reconciliation, breaches and compliance metrics. | Requires corrected canonical identifiers, integration reconciliation, case processing and regulatory timelines. | Partner safety integration | No canonical module identity. MOD-0040 dependency is currently boundary-blocked. | GOVERNANCE-GATED / IDENTITY-RISK. | Resolve MOD-0040 first; approve ownership and partner-exchange contract. | Planning only until identity and SoR decisions.
15 | Next stage — W-5G | Canonical FU/module required | PASS Oversight | Manage post-authorisation study commitments, protocols, milestones, status, safety outputs, regulatory communications and results. | Requires risk-management decisions and integration with relevant study-management capabilities. | Post-authorisation surveillance | No canonical module identity and no code-readiness evidence in supplied reports. | GOVERNANCE-GATED. | Map to existing study modules or approve a PV-specific FU/module; then perform readiness audit. | Planning only until governance decision.
16 | Next stage — W-5H | Canonical FU/module required | Safety Communication and Labeling Linkage | Convert confirmed safety decisions into labeling changes, DHPC/safety communications, approvals, controlled distribution and effectiveness evidence. | Requires MOD-0234 decisions, approved risk controls and labeling/change-control integration. | Regulatory safety action | No canonical module identity and no code-readiness evidence in supplied reports. | GOVERNANCE-GATED. | Approve cross-module ownership: PV owns safety decision; labeling module owns label change. | Planning only until governance decision.
17 | Next stage — W-5I | Canonical FU/module required | Reference Safety Information and Special Situations | Govern reference safety information, expectedness sources, effective dates and regional applicability. Support pregnancy, paediatric, overdose, misuse, medication error, lack of efficacy and other special situations. | Requires product master, labeling, full MOD-0230/MOD-0231 processing and MOD-0234 surveillance contracts. | PV reference and specialised surveillance | No canonical module identity and no code-readiness evidence in supplied reports. | GOVERNANCE-GATED. | Approve SoR for reference safety information and determine which special situations are MOD-0230/0231 extensions. | Planning only until governance decision.
Platform Foundation Readiness — Evidence-Based Input to Seq. 1
Module | Actual status | Completion % | Production readiness % | PV readiness | Main blocker | Recommendation | PV plan use
MOD-0004 | SPECIFICATION_ONLY | 5–10% | 0% | NOT_AVAILABLE | No code; prerequisite registries absent | DO_NOT_USE_YET | Build minimum metric/semantic registry inside Seq. 1 before MOD-0234 runtime
MOD-0018 | PARTIALLY_IMPLEMENTED | 62–75% | 55% | FOUNDATION_AVAILABLE | ABAC/data-scope and admin UI missing | HARDEN_BEFORE_USE | Reuse RBAC core; add pv.* permissions and data-scope controls
MOD-0019 | NOT_IMPLEMENTED | 8–15% | 0% | NOT_AVAILABLE | No masking policy engine | IMPLEMENT_MISSING_FLOW — P0 | Stop-ship for any patient/reporter PII PV flow
MOD-0021 | IMPLEMENTED_BUT_RUNTIME_NOT_PROVEN | 70–80% | 55% | FOUNDATION_AVAILABLE | Tamper-evidence and authenticated smoke missing | HARDEN_BEFORE_USE | Reuse after non-repudiation/tamper controls and runtime proof
MOD-0023 | PARTIALLY_IMPLEMENTED | 60–72% | 50% | FOUNDATION_AVAILABLE | Dedicated golden-flow smoke and designer UI maturity | HARDEN_BEFORE_USE | Reuse workflow runtime after PV-specific transition smoke
MOD-0028 | PARTIALLY_IMPLEMENTED | 68–78% | 55% | FOUNDATION_AVAILABLE | FU06 Mongo partial-index startup blocker | HARDEN_BEFORE_USE | Reuse controlled documents after FU06 fix and runtime proof
MOD-0031 | SPECIFICATION_ONLY | 8–12% | 0% | CONTRACT_ONLY | No runtime code; pack only | COMPLETE_FOUNDATION | Build canonical evidence-linking MVP before PV evidence workflows
MOD-0040 | FOUNDATION_ONLY / WRONG_BOUNDARY | 25–35% | 25% | FOUNDATION_AVAILABLE | Registry identity conflict; canonical/external ID model absent | REBUILD_BOUNDARY | Resolve CONF-01, then build canonical/external ID mapping
MOD-0063 | SPECIFICATION_ONLY | 5% | 0% | NOT_AVAILABLE | No code; Data Contract Registry absent | DO_NOT_USE_YET | Build minimum governed analytical dataset/lineage slice for signals
Evidence basis: platform-modules-final-status-report.md, platform-modules-capability-matrix.md and platform-modules-current-state-report.md, dated 2026-08-03. The audit is based on static repository evidence. dotnet tests and authenticated runtime smoke were not executed in that audit; file/test existence must not be treated as PASS.
| Priority | Module | Current position | Improvements required | PV-specific requirement | Completion / exit gate
| 1 | MOD-0040 — Canonical ID & Correlation Standard | Foundation-only; registry identity conflicts with the canonical Blueprint definition | First resolve the registry conflict through Enterprise Architecture governance. Create an approved MOD-0040 module pack. Implement canonical object IDs, external-reference mappings, source-system identifiers, correlation propagation, trace stitching, duplicate/conflict controls, and API/event contract tests across services. | Provide stable identifiers for Safety Case, Event, Reporter, Product, Signal, SAE, Submission and external Argus/ArisG references. | Registry and Blueprint are aligned; one external identifier cannot resolve to multiple canonical records; the same correlation ID is visible across gateway, API, event, audit and background-job execution.
| 2 | MOD-0019 — Data Masking & Row/Field Security | Not implemented; current helper functions provide log redaction only | Build a real policy engine with field classification, masking policies, row/field rules, role and purpose bindings, server-side query enforcement, response-serialization masking, export controls, policy simulation and a test harness. Add management APIs and an administration UI. | Classify and protect patient, reporter, contact, medical narrative and confidential assessment fields. Verify that UI, API, export, logs, traces and audit payloads apply the same policy. | A restricted PV user receives masked data from both UI and API; an authorized medical reviewer receives approved full values; unauthorized cross-tenant and cross-scope access is denied server-side.
| 3 | MOD-0031 — Evidence Linking Service | Specification and module-pack only; no runtime implementation | Implement the canonical EvidenceLink, EvidenceBundle and EvidenceRequirement systems of record. Add version-specific object-to-evidence links, provenance, integrity validation, coverage queries, adoption/supersession impact, APIs/events, RBAC, audit and UI surfaces. | Support links from cases, signals, assessments, committee decisions, CAPAs and submissions to controlled evidence without storing duplicate documents inside PV modules. | Create link → reload → view provenance → replace evidence version → retain history → include in audit/export pack. Data survives L3 cold-start replay.
| 4 | MOD-0018 — RBAC/ABAC Authorization | RBAC core is operational; ABAC/data scope and administration are incomplete | Complete the real-data-scope resolver, attribute-based policies and the RBAC administration UI. Add policy explanation, scope simulation, effective-date controls and regression tests for endpoint and record-level authorization. Preserve AuthService as the central permission authority. | Introduce a governed pv.* permission catalogue and data scopes such as tenant, legal entity, product, country, study and assigned-case scope. | PV viewer/editor/medical reviewer/signal reviewer roles are enforced server-side; unauthorized requests return controlled denial; data-scope leakage tests pass across two tenants and two product scopes.
| 5 | MOD-0021 — Audit Trail Service | Broad implementation exists, but runtime proof and cryptographic tamper evidence are missing | Add a cryptographic hash/previous-hash chain or equivalent tamper-evidence mechanism. Define fail-closed behavior for regulated writes when audit append fails. Route remaining local audit publishers through the canonical append path. Complete authenticated runtime smoke, export, retention and outbox-recovery validation. | Audit case creation, coding changes, assessment updates, signal validation, committee decisions, closure/reopening, evidence changes and permission-sensitive access. Avoid clear-text PII in audit payloads. | Audit records contain actor, tenant, UTC timestamp, action, object/version and correlation ID; tampering is detectable; an audit outage cannot leave an unaudited regulated write.
| 6 | MOD-0023 — Workflow Designer | Backend capability is substantial; dedicated end-to-end runtime evidence and designer maturity are incomplete | Complete the workflow designer UI and publishable consumption contracts. Execute dedicated golden-flow testing for definition → version → publish → instance → task → approve/reject/request-information/delegate → history. Validate escalation, SLA, concurrency and invalid transitions. | Configure reusable PV workflows for case triage, medical review, signal validation, signal evaluation, committee decision, quality review and evidence request. PV modules retain their business-state ownership. | A versioned PV workflow can be published, started, completed and reloaded; unauthorized transitions fail; stale-version updates produce a controlled conflict; audit and SLA events are visible.
| 7 | MOD-0028 — Documentation Management | Broad implementation exists; FU06 causes a platform-startup blocker | Fix the Mongo partial-index $ne defect in FU06. Stabilize list, language and evidence-related runtime behaviour. Complete tenant-isolation, permission, persistence and regression checks. Finish checksum/version comparison and ensure document approval uses shared workflow/e-signature services rather than local duplicates. | Store PV source documents and attachments with controlled metadata, versions, classification and retention context. Evidence relationships must be delegated to MOD-0031. | Platform starts cleanly; create/upload/version/reopen flows pass authenticated runtime smoke; tenant isolation and permission checks pass; checksum and version history remain consistent after restart.
| 8 | MOD-0004 — Metric & Semantic Registry | Specification-only; no registry entry, module pack or runtime code | Establish canonical registration and an approved module pack. Implement metric definitions, semantic identifiers, calculation contracts, units, dimensions, certification, ownership, versioning, effective dates, query APIs, RBAC, audit and a minimal administration UI. | Define certified Signal Management and PV Quality metrics so MOD-0234 does not hard-code metric formulas or meanings. | Metric definition → calculation contract → certification → reload → consumer query works at runtime, with version and owner traceability.
| 9 | MOD-0063 — Data Warehouse / Lakehouse | Specification-only; no pack or implementation | Create an approved module pack and minimum analytical vertical slice: dataset registry, data contracts, ingestion run history, schema/version validation, ACLs, retention, lineage, quality checks, replay, query access and operational monitoring. Do not use the lakehouse as the Safety Case system of record. | Deliver a governed PV signal dataset containing approved case/event/product/coding/assessment projections, source timestamps, freshness and quality status. | Contract-bound ingestion persists data, rejects invalid schemas, records lineage and run history, enforces tenant/data ACLs, and provides a qualified dataset to MOD-0234.

## Treasury Core Capability Stack
|  | # | Module ID | Module / Capability | Readiness % | Key Evidence | Notes
|  | 1 | MOD-0002 | Interface Registry | 0% | Not in repo | —
|  | 2 | MOD-0003 | Data Contract Registry | 0% | Not in repo | AuthService admin routes functional | 11 commits + 35 reports incl. release-readiness + production-cutover-readiness
|  |  | MOD-0004 | Metric & Semantic Registry | 0% |  | Browser CORS preflight gap | 7 commits incl. contract-alignment-v1-surface + canonical-tree workspace + baseline catalog UI + governance ops; 8 reports
|  | 3 | MOD-0008 | Module Catalog Assignable Expose | 35% | Planning docs only | Catalog alignment proven | Only 1 commit on this branch but 82 reports (ranges batch-00..batch-10+) — work is on another branch; consistent with "ready" status
|  | 4 | MOD-0009 | Tenant Registry Lifecycle Events | 30% | Partial domain modeling | Foundation closure PASS
| NY | 5 | MOD-0018 | Authorization / RBAC | 67% | MOD-0018-authorization-readiness-audit-v4.md verdict Partial; routes + tests present | —
| NY | 6 | MOD-0021 | Audit Explorer / Trail | 40% | MOD-0021-audit_trail-readiness-audit-v4.md; Mongo persist + 20 tests pass | Reference only
| NY | 7 | MOD-0023 | Workflow Designer | 55% | mod0023-workflow-readiness-inspection.md BLOCKED; 6 routes, Save Draft is stub | Reference only
|  | 8 | MOD-0026 | Background Job Scheduler | 0% | Not in repo
|  | 9 | MOD-0027 | Notification / Email Service | 0% | Worker tenancy context issue; no impl | No backend
| NY | 10 | MOD-0028 | Document / Evidence Metadata | 82% | services/Diten.Platform/.../Mod0028/; collection + API + tests pass | Contracts incomplete
| NY | 11 | MOD-0031 | Evidence Linking | 78% | mod0031-openapi-schema-parity-audit-v5.md; dispatcher + outbox runtime-proven | Golden flow not runtime-proven
|  | 12 | MOD-0032 | API Gateway Hardening | 50% | Ocelot config + MOD-0289/0269 live smoke closures | Live sink proof blocked
|  | 13 | MOD-0035 | Event Bus / Internal Events | 30% | In-process events only | Template persistence missing
|  |  | MOD-0037 | Integration Monitoring & Reconciliation | 0% |  | —
|  | 14 | MOD-0039 | Schema Compatibility Governance | 0% | Not in repo | —
|  | 15 | MOD-0041 | Logging / Monitoring | 35% | Health + correlation IDs wired | Lifecycle partial
|  | 16 | MOD-0043 | Tenant Architecture Foundation | 85% | Multi-tenancy proven in MOD-0289 live smoke | Contract closure done
|  | 17 | MOD-0044 | Tenant Manager | 85% | Wired + isolation proven | CORS/login plumbing gaps
|  | 18 | MOD-0046 | Tenant Core UI | 85% | Frontend layout + authenticated routes work | No external broker
|  | 19 | MOD-0046+ | Tenant Core UI Extensions | 50% | Partial menu/page wiring
| NY | 20 | MOD-0048 | Reference Data / Lookups | 80% | mod0048-final-readiness-after-governance-v5.md READY w/ waivers; gateway routes live | —
| NY | 21 | MOD-0057 | Taxonomy / Semantic Tagging | 76% | mod0057 B5 residual closure rerun; 72/72 DataTable pass | No dashboards
not started |  |  | MOD-0118 | General Ledger |  |  | Runtime-proven
| NY | 22 | MOD-0119 | Accounts Payable Source Schedule | 88% | MOD0119-FOUNDATION-CLOSURE-M1-report.md PASS 2026-05-12; 14 routes, 493 LOC | Live gateway smoke PASS
| NY | 23 | MOD-0120 | Accounts Receivable Source Schedule | 88% | MOD0120-SPEC-INSPECTION-M1-report.md Mockup PASS, Production BLOCKED | —
not started | NY |  | MOD-0121 | Bank Reconciliation | 0% |  | Some flags missing
not started | NY | 24 | MOD-0122 | Bank Statement Actuals / Thin Actuals | 15% | Partial treasury refs; no closure | Catalog alignment fixed
| NY | 25 | MOD-0124 | Cash Positioning | 94% | MOD0124-PATH-GATE-M1-readiness-remediation.md BLOCKED; controller + threshold tests pass | Immutability/idempotency proven
not started | NY | 26 | MOD-0125 | Cash Forecasting / 13-week | 28% | Refs only, no impl | Treasury suite green
| NY | 27 | MOD-0126 | Payment Proposals / Approvals | 86% | MOD0126-EVIDENCE-AUDIT-M1-report.md CONDITIONAL PASS; MOD-0031 evidence integrated | Frontend prototype only
not started | NY |  | MOD-0127 | FX Exposure Management | 0% |  | 0
not started | NY |  | MOD-0128 | Tax / VAT / Withholding | 0% |  | Placeholder scope
| NY | 28 | MOD-0140 | Supplier Onboarding / Master | 78% | foundation-proof-closure-summary-v5 CONDITIONAL GO; pass-ready proof | Service placement decision open
not started |  |  | MOD-0141 | Procurement commitment source |  |  | —
not started |  |  | MOD-0142 | Receiving / GRN control sourc |  |  | Treasury suite green
not started | NY |  | MOD-0143 | Invoice Capture & 3-Way Match | 0%
not started | NY | 29 | MOD-0146 | Payment Run Support | 22% | Minimal refs | 5
| NY |  | MOD-0149 | Customer 360 / Account Hierarchy | 91% |  | Compile blocker resolved
not started | NY |  | MOD-0168 | Order Capture | 0%
not started | NY |  | MOD-0169 | Billing & Invoicing | 0% |  | —
not started |  |  | MOD-0171 | Disputes / Claims
| NY | 30 | MOD-0217 | Contract Lifecycle | 72% | foundation-proof-closure-summary-v5 CONDITIONAL GO; preflight runtime proof | Δ
| NY | 31 | MOD-0220 | Legal Entities | 88% | mod0220-final-readiness-v5.md READY w/ 3 P3 waivers; create golden flow live
| NY | 32 | MOD-0266 | Blob / File Storage Provider | 96% | Not in repo | MOD-0048 catalog aligned
| NY | 33 | MOD-0269 | Banks / SWIFT / Payments Gateway | 84% | mod0289-mod0269-release-packaging-manifest live gateway smoke PASS | Browser flow PASS
| NY | 34 | MOD-0289 | Bank Master & Account Registry | 87% | MOD-0289 batch-99 closure FULL GO w/ formal waivers; 75+ batches | —
not started | NY |  | MOD-0291 | Financial Dimensions | 0% |  | Protected reference contract closed
|  | 35 | MOD-0297 | Tenant Subscription Lifecycle | 80% | Proven in multi-tenant closures | API/release/Ocelot all PASS
|  | 36 | MOD-0298 | Tenant Module Entitlement | 87% | Entitlement enforced at gateway/platform | 15
|  | 37 | NEW-001 | Secrets Management | 0% | Not in repo | Runtime-proven
|  | 38 | NEW-002 | Platform Administrators Mgmt | 85% | Admin seeding + RBAC proven | Runtime-tested | Evidence
|  | 39 | PSS-004 | Tenant Login & Security | 75% | Auth service login + gateway path live | 2 | 3 commits + 9 reports incl. default-taxonomy-register-seed (re-run 2026-05-24)
|  | 40 | PSS-005 | Module Catalog | 92% | MOD-0048 catalog seed + 72/72 contract | 0 | 1 commit on branch + 6 reports; status unchanged from foundation audit
|  | 41 | PSS-006 | Subscription Plan Catalog | 95% | Plan provisioning wiring proven | 0 | 1 commit on branch + 3 reports
|  | 42 | PSS-007 | Subscription Feature Management | 90% | Feature flags + MOD-0298 gates enforced | 0 | 0 commits on branch + 3 reports
[7 empty] | 2 | 1 commit on branch (the MOD-0266 auth-seed catalog extension at d9f0cd23 added 21 keys) + 4 reports
[7 empty] | 0 | 2 commits + 3 reports
[7 empty] | 0 | 1 commit + 1 report
[7 empty] | 0 | 0 commits + 1 report (only the foundation pack); still essentially un-started
[7 empty] | 0 | 0 commits + 0 reports + no module-pack file located
[7 empty] | 0 | 0 commits + 0 reports + no module-pack file located
[7 empty] | 0 | 0 commits on branch + 3 reports (foundation audit only); no module-pack file located
|  |  | Wave | Modules that can be developed in parallel
|  |  | Wave 1 | MOD-0149, MOD-0128, MOD-0291, MOD-0122, MOD-0146, MOD-0127
|  |  | Wave 2 | MOD-0168, MOD-0143, MOD-0122, MOD-0146, MOD-0127
|  |  | Wave 3 | MOD-0169, MOD-0121, MOD-0125-M0
|  |  | Wave 4 | MOD-0125 full build
|  |  | Wave 5 | Cross-module hardening: MOD-0121, MOD-0122, MOD-0125, MOD-0146, MOD-0127

## RA DLE
RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK
RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK | RA DLE SCOPE — MERGED INTO INTEGRATED R&D–RA LIFECYCLE MANAGEMENT BLOCK
All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix
All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix
All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix
All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix
All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix | All required RA development capabilities are governed through the Integrated R&D–RA Lifecycle Management Block. Primary management sheet: Optimized Master Plan Detailed technical backlog: R&D-RA Dev Requirements Architecture registers: Software Capability Matrix, Interface Registry, Shared Evidence Matrix

## HR & TEP
| Release | Capability Block | Lane | Module Code | Module Name | Type | Output / Role
Done | R0 | Platform Backbone + HR Source Readiness | R0-A | MOD-0018 | RBAC / Authorization | Backbone readiness | HR and TEP permission control
Done | R0 | Platform Backbone + HR Source Readiness | R0-A | MOD-0021 | Audit Trail | Backbone readiness | Access, change, export, approval audit
| R0 | Platform Backbone + HR Source Readiness | R0-A | MOD-0030 | Records Management / Retention / Legal Hold | Backbone readiness | HR/TEP retention and legal hold
Done | R0 | Platform Backbone + HR Source Readiness | R0-B | MOD-0023 | Workflow | Backbone readiness | Approval, dispute, review workflows
Done | R0 | Platform Backbone + HR Source Readiness | R0-B | MOD-0028 | Documentation & Evidence Management | Backbone readiness | Internal evidence/document storage
Done | R0 | Platform Backbone + HR Source Readiness | R0-B | MOD-0031 | Evidence Linking Service | Backbone readiness | Link evidence to HR/TEP objects
Done | R0 | Platform Backbone + HR Source Readiness | R0-C | MOD-0048 | Reference Data / Lookups | Backbone readiness | HR/TEP controlled values
Done | R0 | Platform Backbone + HR Source Readiness | R0-C | MOD-0057 | Taxonomy / Semantic Tagging | Backbone readiness | Skills, roles, categories, tags
| R0 | Platform Backbone + HR Source Readiness | R0-D | MOD-0251 | Core HR / Employee Master | Native HCM master readiness | Employee legal profile, employment status, job/employment record
| R0 | Platform Backbone + HR Source Readiness | R0-D | MOD-0279 | Native Payroll Engine | Native HCM payroll readiness | Payroll calculation, payroll runs, payroll results
| R0 | Platform Backbone + HR Source Readiness | R0-D | MOD-0280 | Time, Attendance & Leave Management | Native HCM time/leave readiness | Time entries, attendance, leave balances, schedules
| R0 | Platform Backbone + HR Source Readiness | R0-D | MOD-0281 | Payroll Governance & Payroll Controls | Native HCM payroll governance readiness | Payroll controls, approvals, exceptions, governance
Ali | R0 | Platform Backbone + HR Source Readiness | R0-D | MOD-0288 | Organization, Person & Position Directory | Native HCM / platform directory readiness | Internal person/org/position foundation
| R1 | Human Capital Management Foundation MVP | R1-A | MOD-0297 | HR Capability Block Shell | Native HCM MVP | HR workspace shell
| R1 | Human Capital Management Foundation MVP | R1-A | MOD-0298 | Employee Profile Workspace | Native HCM MVP | Employee profile workspace over internal employee master
| R1 | Human Capital Management Foundation MVP | R1-B | MOD-0299 | Position & Organization Assignment | Native HCM MVP | Employee-position-org-manager assignment
| R1 | Human Capital Management Foundation MVP | R1-C | MOD-0314 | HR Governance & Sensitive Access Controls | Native HCM governance | HR-sensitive visibility and access rules
| R1 | Human Capital Management Foundation MVP | R1-D | MOD-0305 | Offboarding & Exit Management | Native HCM MVP | Governed offboarding + TEP handoff payload
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-A | MOD-0321 | Talent Ecosystem Platform Shell | TEP MVP | TEP workspace shell
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-A | MOD-0323 | Association Membership & Member Company Registry | TEP MVP | Association/company membership registry
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-A | MOD-0324 | Verified HR Participant & Company Access | TEP MVP | Verified HR/company access
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-B | MOD-0325 | Consent, Visibility & Access Policy | TEP MVP | Consent and visibility rules
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-B | MOD-0326 | Talent Ecosystem Governance & Review Board | TEP MVP | Review board workflow
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-B | MOD-0330 | Trust Level & Multi-Signature Engine | TEP MVP | Trust level validation
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-C | MOD-0322 | Industry Candidate Identity & Talent Profile | TEP MVP | Sector candidate identity
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-D | MOD-0327 | Industry Exit Reference Record Registry | TEP MVP | Cross-company exit reference records
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-D | MOD-0328 | Reference Exchange Marketplace | TEP MVP | HR-to-HR reference exchange
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-D | MOD-0329 | Rehire Recommendation Network | TEP MVP | Rehire recommendation
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-D | MOD-0331 | Candidate Response & Dispute Management | TEP MVP | Candidate response/dispute flow
Ali | R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-E | MOD-0027 | Notification | Backbone extension | HR/candidate/reference notifications
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-E | MOD-0263 | Notification Delivery Service | Backbone extension | Internal notification delivery channel
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-E | MOD-0029 | Controlled Documents | Backbone extension | Reference templates and controlled policies
| R2 | Industry Talent Ecosystem Platform — Reference Network MVP | R2-E | MOD-0262 | Internal Document Repository Service | Backbone extension | Internal document repository support for evidence/reference packages
| R3 | Human Capital Management Foundation Completion | R3-A | MOD-0300 | Recruitment / Applicant Intake | HCM completion | Applicant intake
| R3 | Human Capital Management Foundation Completion | R3-A | MOD-0301 | Candidate Pipeline & Interview Management | HCM completion | Recruiting pipeline and interviews
| R3 | Human Capital Management Foundation Completion | R3-A | MOD-0302 | Offer Management | HCM completion | Offer workflow
| R3 | Human Capital Management Foundation Completion | R3-A | MOD-0303 | Employee Onboarding | HCM completion | Onboarding lifecycle
| R3 | Human Capital Management Foundation Completion | R3-B | MOD-0304 | Employment Change / Transfer / Promotion | HCM completion | Internal role-change workflow
| R3 | Human Capital Management Foundation Completion | R3-C | MOD-0306 | Performance Review Management | HCM completion | Performance reviews
| R3 | Human Capital Management Foundation Completion | R3-C | MOD-0307 | Competency & Skills Assessment | HCM completion | Skills/competency assessments
| R3 | Human Capital Management Foundation Completion | R3-C | MOD-0308 | Development Plan Management | HCM completion | Development plans
| R3 | Human Capital Management Foundation Completion | R3-C | MOD-0309 | Learning / Training Records | HCM completion | Employee training records
| R3 | Human Capital Management Foundation Completion | R3-C | MOD-0320 | Succession & High-Potential Tracking | HCM completion | Succession and HiPo tracking
| R3 | Human Capital Management Foundation Completion | R3-D | MOD-0310 | Workforce Planning | HCM completion | Workforce planning
| R3 | Human Capital Management Foundation Completion | R3-D | MOD-0311 | Headcount & Position Budget Planning | HCM completion | Headcount and position budget
| R3 | Human Capital Management Foundation Completion | R3-E | MOD-0312 | HR KPI & Analytics Facade | HCM completion | HR KPI facade over shared analytics
| R3 | Human Capital Management Foundation Completion | R3-E | MOD-0313 | HR Documentation & Evidence Workspace | HCM completion | HR workspace over shared docs/evidence
| R3 | Human Capital Management Foundation Completion | R3-E | MOD-0315 | Time, Attendance & Leave Workspace | HCM completion | HR/manager workspace over internal time, attendance, and leave records
| R3 | Human Capital Management Foundation Completion | R3-E | MOD-0316 | Compensation & Benefits Management | Native HCM compensation | Compensation packages, benefits assignments, compensation reference data
| R3 | Human Capital Management Foundation Completion | R3-E | MOD-0319 | Employee / Manager Self-Service Channel | HCM completion | Employee/manager interaction channel
| R3 | Human Capital Management Foundation Completion | R3-F | MOD-0317 | Employee Relations & HR Case Management | HCM completion | Grievance, disciplinary, investigation cases
| R3 | Human Capital Management Foundation Completion | R3-F | MOD-0318 | HR Compliance & Statutory Reporting | HCM completion | HR compliance reporting
| R3 | Human Capital Management Foundation Completion | R3-G | MOD-0004 | Metric & Semantic Registry | Analytics backbone | Metric semantic governance
| R3 | Human Capital Management Foundation Completion | R3-G | MOD-0059 | KPI Catalog | Analytics backbone | KPI catalog
| R3 | Human Capital Management Foundation Completion | R3-G | MOD-0060 | Metric Definitions & Ownership | Analytics backbone | Metric definitions and ownership
| R3 | Human Capital Management Foundation Completion | R3-G | MOD-0061 | Scorecards / Dashboards | Analytics backbone | HR/TEP dashboard layer
| R3 | Human Capital Management Foundation Completion | R3-G | MOD-0062 | Baseline & Experiment Measurement | Analytics backbone | Program impact measurement
| R3 | Human Capital Management Foundation Completion | R3-G | MOD-0063 | Data Warehouse / Lakehouse | Analytics backbone | Data foundation
| R3 | Human Capital Management Foundation Completion | R3-G | MOD-0064 | ETL / ELT Pipelines | Analytics backbone | Data pipeline foundation
| R4 | Industry Talent Ecosystem Platform Completion | R4-A | MOD-0332 | Hiring Risk Indicators | TEP completion | Rule-based hiring risk signals
| R4 | Industry Talent Ecosystem Platform Completion | R4-A | MOD-0333 | Early Warning Signals | TEP completion | Cross-company pattern detection
| R4 | Industry Talent Ecosystem Platform Completion | R4-A | MOD-0334 | Restricted Integrity Registry | TEP completion | Serious restricted integrity cases
| R4 | Industry Talent Ecosystem Platform Completion | R4-B | MOD-0335 | Professional Reputation Ledger | TEP completion | Positive professional reputation signals
| R4 | Industry Talent Ecosystem Platform Completion | R4-B | MOD-0336 | Talent Data Foundation | TEP completion | Talent data foundation
| R4 | Industry Talent Ecosystem Platform Completion | R4-C | MOD-0337 | Industry Talent Pool | TEP completion | Trusted talent pool
| R4 | Industry Talent Ecosystem Platform Completion | R4-C | MOD-0338 | Industry Skill Passport | TEP completion | Verified skill passport
| R4 | Industry Talent Ecosystem Platform Completion | R4-C | MOD-0339 | Candidate Career Passport | TEP completion | Career passport
| R4 | Industry Talent Ecosystem Platform Completion | R4-C | MOD-0340 | Talent Development Network | TEP completion | Talent development pathways
| R4 | Industry Talent Ecosystem Platform Completion | R4-C | MOD-0341 | Industry Succession Pool | TEP completion | Sector succession pool
| R4 | Industry Talent Ecosystem Platform Completion | R4-C | MOD-0342 | Verified Certification Registry | TEP completion | Verified certifications
| R4 | Industry Talent Ecosystem Platform Completion | R4-C | MOD-0343 | Mentorship & Recommendation Network | TEP completion | Mentorship/recommendation network
| R4 | Industry Talent Ecosystem Platform Completion | R4-D | MOD-0344 | Shared Salary Benchmarking | TEP completion | Sector salary benchmarking from internal payroll/compensation data
| R4 | Industry Talent Ecosystem Platform Completion | R4-D | MOD-0345 | Workforce Analytics | TEP completion | Workforce analytics
| R4 | Industry Talent Ecosystem Platform Completion | R4-D | MOD-0346 | Sector Talent Trends | TEP completion | Sector talent trends
| R4 | Industry Talent Ecosystem Platform Completion | R4-D | MOD-0347 | Talent Supply & Demand Forecasting | TEP completion | Talent supply/demand forecasting
| R4 | Industry Talent Ecosystem Platform Completion | R4-D | MOD-0348 | Skills Gap Heatmap | TEP completion | Skills gap intelligence
| R4 | Industry Talent Ecosystem Platform Completion | R4-D | MOD-0349 | Sector Mobility Intelligence | TEP completion | Talent mobility intelligence
| R4 | Industry Talent Ecosystem Platform Completion | R4-E | MOD-0350 | Association Operations | TEP completion | Association operating workflows
| R4 | Industry Talent Ecosystem Platform Completion | R4-E | MOD-0351 | Industry Knowledge Network | TEP completion | Knowledge library/community layer

## Sheet1
Seq | Priority | Release | Capability Block | Lane | Capability Area | Module Code | Module Name | Type
1 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-A | Platform Backbone / Security | MOD-0018 | RBAC / ABAC Authorization | Required Dependency
2 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-A | Platform Backbone / Audit | MOD-0021 | Audit Trail Service | Required Dependency
3 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-A | Platform Backbone / Workflow | MOD-0023 | Workflow Designer | Required Dependency
4 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-A | Platform Backbone / Approval Control | MOD-0022 | e-Signature Service | Required Dependency
5 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-B | Platform Backbone / Evidence | MOD-0028 | Documentation & Evidence Management | Required Dependency
6 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-B | Platform Backbone / Controlled Docs | MOD-0029 | Controlled Documents | Required Dependency
7 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-B | Platform Backbone / Records | MOD-0030 | Records Management | Required Dependency
8 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-B | Platform Backbone / Evidence Linking | MOD-0031 | Evidence Linking Service | Required Dependency
9 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-C | Platform Backbone / Traceability | MOD-0040 | Canonical ID & Correlation Standard | Required Dependency
10 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-C | Data Backbone / Reference Data | MOD-0048 | Reference Data Management | Required Dependency
11 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-C | Data Backbone / Taxonomy | MOD-0057 | Semantic Tagging & Taxonomy Management | Required Dependency
12 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-D | Master Data Backbone | MOD-0290 | Product / Item / SKU Master | Master Readiness
13 | P0 | R0 | Platform Backbone + SCQ Source Readiness | R0-D | Procurement / Supplier Master | MOD-0140 | Supplier Onboarding | Master Readiness
14 | P1 | R1 | Procurement / Purchasing / P2P Foundation MVP | R1-A | Procurement / Sourcing | MOD-0145 | Sourcing / RFQ / RFP | Core MVP
15 | P1 | R1 | Procurement / Purchasing / P2P Foundation MVP | R1-A | Procurement / Purchasing | MOD-0141 | Requisition & Purchase Orders | Core MVP
16 | P2 | R1 | Procurement / Purchasing / P2P Foundation MVP | R1-A | Procurement / Contracts | MOD-0144 | Contracting & Clause Library | Core / Legal Bridge
17 | P1 | R1 | Procurement / Purchasing / P2P Foundation MVP | R1-B | Procurement / Receiving | MOD-0142 | Receiving / GRN | Core MVP
18 | P1 | R1 | Procurement / Purchasing / P2P Foundation MVP | R1-B | Procurement / Invoice Control | MOD-0143 | Invoice Capture & 3-Way Match | Core MVP
19 | P2 | R1 | Procurement / Purchasing / P2P Foundation MVP | R1-B | Procurement / Payment Bridge | MOD-0146 | Payment Run Support | Conditional Bridge
20 | P2 | R1 | Procurement / Purchasing / P2P Foundation MVP | R1-C | Procurement / Supplier Governance | MOD-0147 | Supplier Performance & Risk | Core Completion
21 | P2 | R1 | Procurement / Purchasing / P2P Foundation MVP | R1-C | Procurement / Supplier Collaboration | MOD-0148 | Supplier Portal | Optional Extension
22 | P1 | R2 | Inventory / Warehouse / Traceability MVP | R2-A | Inventory / Ledger | MOD-0173 | Inventory Ledger & Valuation | Core MVP
23 | P1 | R2 | Inventory / Warehouse / Traceability MVP | R2-A | Inventory / Traceability | MOD-0174 | Lot / Batch / Serial Tracking | Core MVP
24 | P1 | R2 | Inventory / Warehouse / Traceability MVP | R2-B | Inventory / Quality Hold | MOD-0175 | Quarantine / Blocked Stock | Core MVP
25 | P1 | R2 | Inventory / Warehouse / Traceability MVP | R2-B | Inventory / FEFO | MOD-0176 | Expiry / FEFO Management | Core MVP
26 | P2 | R2 | Inventory / Warehouse / Traceability MVP | R2-B | Inventory / Recall | MOD-0177 | Recall Readiness | Core Completion
27 | P1 | R2 | Inventory / Warehouse / Traceability MVP | R2-C | Warehouse / Execution | MOD-0178 | Putaway / Picking / Packing | Core MVP
28 | P2 | R2 | Inventory / Warehouse / Traceability MVP | R2-C | Warehouse / Control | MOD-0181 | Cycle Counting | Core Completion
29 | P2 | R2 | Inventory / Warehouse / Traceability MVP | R2-C | Warehouse / Scanning | MOD-0182 | Barcode / RFID | Core Completion
30 | P2 | R2 | Inventory / Warehouse / Traceability MVP | R2-D | Warehouse / External Integration | MOD-0179 | 3PL Integration | Integration Bridge
31 | P2 | R2 | Inventory / Warehouse / Traceability MVP | R2-D | Warehouse / Planning | MOD-0180 | Wave Planning | Core Completion
32 | P1 | R3 | QC / LIMS / QMS Release Governance MVP | R3-A | QMS / Document Control | MOD-0206 | Document Control | Core MVP
33 | P1 | R3 | QC / LIMS / QMS Release Governance MVP | R3-A | QMS / Change Control | MOD-0209 | Change Control | Core MVP
34 | P1 | R3 | QC / LIMS / QMS Release Governance MVP | R3-A | QMS / Nonconformance | MOD-0207 | Deviations / Nonconformances | Core MVP
35 | P1 | R3 | QC / LIMS / QMS Release Governance MVP | R3-A | QMS / CAPA | MOD-0208 | CAPA | Core MVP
36 | P1 | R3 | QC / LIMS / QMS Release Governance MVP | R3-B | QC / LIMS | MOD-0202 | Sample Management | Core MVP
37 | P1 | R3 | QC / LIMS / QMS Release Governance MVP | R3-B | QC / LIMS | MOD-0203 | Test Results & CoA | Core MVP
38 | P2 | R3 | QC / LIMS / QMS Release Governance MVP | R3-B | QC / Stability | MOD-0204 | Stability Studies | Core Completion
39 | P2 | R3 | QC / LIMS / QMS Release Governance MVP | R3-B | QC / Analytics | MOD-0205 | Trend Analysis | Core Completion
40 | P1 | R3 | QC / LIMS / QMS Release Governance MVP | R3-C | Supplier Quality | MOD-0210 | Supplier Quality | Core MVP
41 | P2 | R3 | QC / LIMS / QMS Release Governance MVP | R3-C | Quality / Complaints | MOD-0211 | Complaints & Investigations | Optional Core
42 | P1 | R4 | Supply Chain Planning / Logistics Completion | R4-A | Planning / Demand | MOD-0188 | Demand Planning | Core MVP
43 | P1 | R4 | Supply Chain Planning / Logistics Completion | R4-A | Planning / Replenishment | MOD-0189 | MRP & Replenishment | Core MVP
44 | P2 | R4 | Supply Chain Planning / Logistics Completion | R4-A | Planning / Inventory Policy | MOD-0191 | Safety Stock Optimization | Core Completion
45 | P2 | R4 | Supply Chain Planning / Logistics Completion | R4-A | Planning / Governance | MOD-0190 | S&OP Workflow & Sign-offs | Core Completion
46 | P2 | R4 | Supply Chain Planning / Logistics Completion | R4-A | Planning / Capacity | MOD-0192 | Capacity Planning | Optional Core
47 | P1 | R4 | Supply Chain Planning / Logistics Completion | R4-B | Logistics / Shipment Visibility | MOD-0183 | Shipment Tracking & POD | Core MVP
48 | P2 | R4 | Supply Chain Planning / Logistics Completion | R4-B | Logistics / Carrier | MOD-0184 | Carrier Management | Core Completion
49 | P2 | R4 | Supply Chain Planning / Logistics Completion | R4-B | Logistics / Routing | MOD-0185 | Routing & Load Planning | Core Completion
50 | P2 | R4 | Supply Chain Planning / Logistics Completion | R4-B | Logistics / Returns | MOD-0186 | Reverse Logistics | Core Completion
51 | P2 | R4 | Supply Chain Planning / Logistics Completion | R4-B | Logistics / Claims | MOD-0187 | Claims Management | Core Completion
52 | P3 | R5 | Adjacent / Conditional Bridges | R5-A | Supplier / Risk Bridge | MOD-0216 | Third-Party Risk Management | Conditional Bridge
53 | P3 | R5 | Adjacent / Conditional Bridges | R5-A | Legal / Contract Bridge | MOD-0217 | Contract Lifecycle Management | Conditional Bridge
54 | P3 | R5 | Adjacent / Conditional Bridges | R5-A | Legal / Clause Bridge | MOD-0218 | Clause Library | Conditional Bridge
55 | P3 | R5 | Adjacent / Conditional Bridges | R5-B | Maintenance / Spare Parts | MOD-0201 | Spare Parts Management | Conditional Bridge
56 | P3 | R5 | Adjacent / Conditional Bridges | R5-B | Manufacturing Dependency | MOD-0193 | BOM & Routings | Conditional Bridge
57 | P3 | R5 | Adjacent / Conditional Bridges | R5-B | Manufacturing Dependency | MOD-0194 | Work Orders | Conditional Bridge
58 | P3 | R5 | Adjacent / Conditional Bridges | R5-B | Manufacturing Dependency | MOD-0195 | Batch Execution / eBR | Conditional Bridge
59 | P3 | R5 | Adjacent / Conditional Bridges | R5-B | Manufacturing Dependency | MOD-0197 | Co-Manufacturer Management | Conditional Bridge

## Supply Chain-Qulaity Cap Block
Wave | Module Code | Module Name | Capability Group | Mandatory Document | Description | AI Governance Assets Required
Wave 0 | MOD-0040 | Canonical ID & Correlation Standard | Backbone / Traceability | SCQ-CB-DOC-001 Capability Block Overview / Charter | Defines block purpose, business value, included modules, excluded modules, MVP vs full scope, sponsors, and success definition. | Capability Block Prompt, Scope Rules, MVP Boundary Rules
Wave 0 | MOD-0022 | e-Signature Service | Backbone / Approval Control | SCQ-CB-DOC-002 Target Operating Model | Defines how Procurement, Inventory, Warehouse, QA, QC, Supplier Quality, and TPRM operate together; includes roles, responsibilities, approval points, and escalation model. | Operating Model Prompt, RACI Rules, Approval Governance Rules
Wave 0 | MOD-0029 | Controlled Documents | Backbone / Controlled Document Lifecycle | SCQ-CB-DOC-003 System Architecture & Boundary Design | Defines technical architecture, module boundaries, consumed backbone services, APIs/events, storage, workflow, audit, document, and evidence architecture. | Architecture Prompt, Boundary Rules, Shared Service Reuse Rules
Wave 0 | MOD-0030 | Records Management / Retention / Legal Hold | Backbone / Records Governance | SCQ-CB-DOC-004 Module Scope & Ownership Map | Lists all 16 business MVP modules + 4 backbone dependencies; defines SoR ownership, consumed services, duplicate-ownership exclusions, and module handoff rules. | SoR Mapping Rules, Ownership Rules, Capability Taxonomy Rules
Wave 1 | MOD-0290 | Product / Item / SKU Master | Master Data / Product Foundation | SCQ-CB-DOC-005 End-to-End Workflow | Defines full operational flow: supplier approval → item/SKU → inventory/lot → quarantine → sample → test result/CoA → release/reject → deviation/CAPA/change → warehouse execution. | Workflow Prompt, State Machine Rules, Golden Flow Rules
Wave 1 | MOD-0173 | Inventory Ledger & Valuation | Inventory | SCQ-CB-DOC-006 Data Model & Object Registry | Defines core objects: item, SKU, lot, inventory movement, quarantine hold, sample, test result, CoA, deviation, CAPA, change request, supplier quality approval, TPRM risk record. | Data Modeling Rules, Object Registry Rules, Data Contract Rules
Wave 1 | MOD-0174 | Lot / Batch / Serial Tracking | Inventory / Traceability | SCQ-CB-DOC-007 Dependency & Integration Map | Defines cross-module dependencies, API/event contracts, consumed Treasury/backbone modules, upstream/downstream systems, and integration constraints. | Interface Contract Prompt, Dependency Analysis Skill, Event/API Rules
Wave 1 | MOD-0206 | Document Control | Quality Assurance / QMS | SCQ-CB-DOC-008 Security, RBAC & Segregation of Duties Matrix | Defines role permissions for procurement, warehouse, QC analyst, QA reviewer, supplier quality, TPRM, admin, approver, and viewer roles. | RBAC Matrix Prompt, SoD Rules, Tenant Isolation Rules
Wave 1 | MOD-0207 | Deviations / Nonconformances | Quality Assurance / QMS | SCQ-CB-DOC-009 Audit, Evidence & Records Policy | Defines audit events, evidence links, CoA evidence, QC release records, CAPA evidence, change-control evidence, and retention/legal-hold requirements. | Audit Rules, Evidence Linking Rules, Records Governance Rules
Wave 1 | MOD-0208 | CAPA | Quality Assurance / QMS | SCQ-CB-DOC-010 Document Control & Versioning Policy | Defines controlled specs, SOPs, test methods, sampling plans, stability protocols, approval states, effective dates, supersession, and change history. | Versioning Rules, Controlled Document Rules, Changelog Rules
Wave 2 | MOD-0175 | Quarantine / Blocked Stock | Inventory / Quality Control | SCQ-CB-DOC-011 Quality Review & Approval Policy | Defines review/approval rules for QC results, CoA, quarantine release, supplier quality approval, CAPA closure, change approval, and stability conclusions. | Human Review Prompt, Approval Rules, e-Signature Compatibility Rules
Wave 2 | MOD-0176 | Expiry / FEFO Management | Inventory / Quality Control | SCQ-CB-DOC-012 Task / Exception / Escalation Policy | Defines how quality findings, failed QC, OOS/OOT, supplier issues, overdue CAPA, blocked stock, and missing evidence create tasks and escalations. | Task Generation Rules, Exception Handling Rules, SLA Rules
Wave 2 | MOD-0202 | Sample Management | Quality Control / LIMS | SCQ-CB-DOC-013 UI / Page-Level Specification | Defines dashboards and pages: item master, inventory ledger, lot detail, quarantine board, sample register, CoA view, deviation register, CAPA board, change register, supplier quality profile. | Page Spec Prompt, UI Rules, UX Acceptance Rules
Wave 2 | MOD-0203 | Test Results & CoA | Quality Control / LIMS | SCQ-CB-DOC-014 Reporting / Export / Release Package Policy | Defines controlled exports: CoA, QC release package, supplier approval package, CAPA summary, change-control package, audit extracts, and inventory/quality reports. | Export Rules, Report Rules, Evidence Package Rules
Wave 2 | MOD-0210 | Supplier Quality | Quality Assurance / Supplier Quality | SCQ-CB-DOC-015 Validation & Test Strategy | Defines scripted testing, negative testing, requirements-to-test traceability, UAT, release evidence, regression testing, and MVP acceptance criteria. | QA Prompt, Test Strategy Rules, Traceability Matrix Rules
Wave 2 | MOD-0216 | Third-Party Risk Management | Procurement / Supplier Risk | SCQ-CB-DOC-016 Execution Plan / Wave Plan | Defines build waves, parallel lanes, sequencing, blockers, readiness gates, module-by-module implementation order, and hardening wave. | Execution Planning Prompt, Sequencing Rules, Parallelization Rules
Wave 2 | MOD-0188 | Demand Planning / Sales Forecast | Planning / Demand Forecasting | SCQ-CB-DOC-017 Acceptance & Risk Register | Defines block-level acceptance criteria, open risks, dependency blockers, compliance risks, integration risks, and release/no-release decision criteria. | Risk Analysis Prompt, Acceptance Rules, Release Gate Rules
Wave 3 | MOD-0204 | Stability Studies | Quality Control / Stability | SCQ-CB-DOC-018 Deployment Checklist & Release Notes | Confirms migrations, routes, feature flags, seed/reference data, smoke tests, rollback, known limitations, and release scope. | Deployment Rules, Rollback Rules, Release Notes Prompt
Wave 3 | MOD-0209 | Change Control | Quality Assurance / QMS
Wave 3 | MOD-0147 | Supplier Performance & Risk | Procurement / Supplier Governance
Wave 3 | MOD-0189 | MRP & Replenishment | Planning / Procurement Planning
Wave 4 | MOD-0178 | Putaway / Picking / Packing | Warehouse Operations
Wave 5 | All 22 relevant modules | Cross-module hardening | Integrated MVP Acceptance
Wave | Modules that can be developed in parallel | Development theme
Wave 0 | MOD-0040, MOD-0022, MOD-0029, MOD-0030 | Backbone foundation: canonical traceability, e-signature, controlled document lifecycle, records retention / legal hold
Wave 1 | MOD-0290, MOD-0173, MOD-0174, MOD-0206, MOD-0207, MOD-0208 | Product/SKU, inventory ledger, lot/batch/serial, QMS document control, deviation/NC, CAPA
Wave 2 | MOD-0175, MOD-0176, MOD-0202, MOD-0203, MOD-0210, MOD-0216, MOD-0188 | Quarantine, expiry/FEFO, QC sample/result, supplier quality approval, third-party risk, demand forecast foundation
Wave 3 | MOD-0204, MOD-0209, MOD-0147, MOD-0189 | Stability studies, change control, supplier performance/risk, MRP and replenishment planning
Wave 4 | MOD-0178 | Warehouse execution: putaway, picking, packing
Wave 5 | Cross-module hardening: MOD-0040, MOD-0022, MOD-0029, MOD-0030, MOD-0147, MOD-0173, MOD-0174, MOD-0175, MOD-0176, MOD-0178, MOD-0188, MOD-0189, MOD-0202, MOD-0203, MOD-0204, MOD-0206, MOD-0207, MOD-0208, MOD-0209, MOD-0210, MOD-0216, MOD-0290 | End-to-end MVP hardening across traceability, approvals, records, controlled documents, supplier quality, TPRM, QC release, stability, QA cases, inventory, demand planning, replenishment, and warehouse execution
Required block-level documents
Level | Mandatory Document | For Supply Chain–Quality Block, this must define
Block | Capability Block Documentation | Scope, purpose, business value, MVP modules, excluded modules, boundaries, ownership, governance rules
Block | Capability Block Execution Plan | Waves, module sequencing, parallel-safe workstreams, blockers, milestones, rollout approach
Block | Capability Block Dependency & Integration Map | Module dependencies, consumed Treasury/backbone services, APIs, events, external integrations, shared services
Block | Capability Block Acceptance & Risk Register | Block readiness criteria, compliance risks, integration risks, open blockers, release conditions
So for this block, you do not need 18 mandatory block documents.
You need 4 block-level governance documents.
1. Capability Block Documentation
Document purpose
This is the main block definition document.
Section | Must include
Block name | Supply Chain–Quality Capability Block
Block purpose | Inventory, warehouse, supplier quality, QC/LIMS, QA/QMS, TPRM, release governance
Business value | Controlled supplier approval, raw material QC, finished product release, traceable inventory, quality governance
MVP module list | The 16 business modules
Backbone dependencies | The 4 minimized backbone modules
Excluded modules | Treasury, finance, platform backbone, P2P modules already developed or in process
Architecture boundary | What this block owns vs consumes
System-of-record ownership | Object → owner module
Governance rules | Audit, evidence, RBAC, SoD, controlled release, document control, retention
MVP success definition | End-to-end controlled flow works and is tested
Output of this document
It becomes the source of truth for module scope.
2. Capability Block Execution Plan
Document purpose
This is the development sequencing document.
Section | Must include
Wave 0 | Backbone dependency enablement
Wave 1 | Product/SKU, inventory ledger, lot/batch/serial, QMS foundation
Wave 2 | Quarantine, FEFO, sample/result, supplier quality, TPRM
Wave 3 | Stability, change control, supplier performance
Wave 4 | Warehouse execution
Wave 5 | Cross-module hardening
Parallel-safe lanes | Which modules can be developed at the same time
Dependencies | What must be completed before each wave
Blockers | Missing contracts, missing backbone capability, unclear ownership
Milestones | Inspection, implementation, integration, hardening, release
Rollout approach | MVP first, full version later
Output of this document
It tells developers what to build first, what can run in parallel, and what must wait.
3. Capability Block Dependency & Integration Map
Document purpose
This is the cross-module contract map.
Section | Must include
Internal dependencies | MOD-0290 → MOD-0173 → MOD-0174 → MOD-0175 → MOD-0202 → MOD-0203 etc.
Consumed Treasury/P2P modules | Supplier master, procurement commitment, receiving/GRN, invoice match, payment, AP, GL, bank master, legal entity
Consumed backbone modules | RBAC, audit, workflow, docs/evidence, event bus, gateway, logging, reference data, taxonomy
Additional backbone modules | MOD-0040, MOD-0022, MOD-0029, MOD-0030
API contracts | Command/query APIs between modules
Event contracts | State-change events such as lot quarantined, sample created, test approved, stock released
Integration risks | Missing contract, schema mismatch, event ownership ambiguity
External systems | LIMS, 3PL, barcode/RFID, ERP, QMS, supplier portal if later in scope
Output of this document
It prevents teams from inventing contracts or duplicating ownership.
4. Capability Block Acceptance & Risk Register
Document purpose
This is the readiness and go/no-go control document.
Section | Must include
Block acceptance criteria | What must be true for MVP to be accepted
Golden flow acceptance | Supplier approval → item/SKU → inventory/lot → quarantine → sample → result/CoA → release/reject → deviation/CAPA/change → WMS
Risk register | Compliance, integration, data, workflow, security, audit, release risks
Known limitations | What is accepted for MVP and what is deferred
Blockers | Open issues preventing development or release
Release conditions | Minimum smoke tests, browser tests, API tests, audit checks, RBAC checks
Negative tests | Permission denial, failed QC, missing evidence, rejected approval, blocked release
Final verdict model | PASS / CONDITIONAL PASS / PARTIAL / BLOCKED / FAIL
Output of this document
It is used to decide whether the block is ready to build, ready to integrate, and ready to release.
Minimum block-level document set
Document Code | Mandatory Block Document | Required before module specs?
SCQ-CB-BLK-001 | Capability Block Documentation | Yes
SCQ-CB-BLK-002 | Capability Block Execution Plan | Yes
SCQ-CB-BLK-003 | Capability Block Dependency & Integration Map | Yes
SCQ-CB-BLK-004 | Capability Block Acceptance & Risk Register | Yes
What must be developed from these block documents?
These 4 block documents must produce the following development inputs:
Development input | Comes from block document
Final MVP module list | Capability Block Documentation
Final excluded module list | Capability Block Documentation
System-of-record ownership map | Capability Block Documentation
Development waves | Execution Plan
Parallel-safe lanes | Execution Plan
Module dependency order | Execution Plan + Dependency Map
API/event contract stubs | Dependency & Integration Map
Consumed backbone/Treasury services | Dependency & Integration Map
Block-level acceptance criteria | Acceptance & Risk Register
Block-level test scope | Acceptance & Risk Register
Known limitations | Acceptance & Risk Register
Release/no-release decision rules | Acceptance & Risk Register
Then module-level specs are developed from them
After the 4 block documents are done, you can generate module-level documents.
For each module, you then create:
Module-level document | Source from block documents
Module Specification | Scope, ownership, workflow, dependencies
Module Development Plan | Execution wave and build sequence
Module API / UI / Data / Integration Specification | Dependency map and data ownership
Module Security & Permission Matrix | Block RBAC / SoD rules
Module Test Plan & Definition of Done | Block acceptance and risk criteria

## Integrated R&D–RA Lifecycle Man
Integrated R&D–RA Lifecycle Management Block — Consolidated Management Plan v5 | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog | Integrated R&D–RA Lifecycle Management Block — Detailed Development Backlog
Management rows are consolidated by canonical Primary Module where ownership and release gates are shared. MOD-0117 combines Packs 1–4; MOD-0206 combines Document Control, source-document approval and Pack 7; MOD-0236 combines dossier, CTD readiness, Pack 9, authority response and submission archive. All original pack-level rows are retained in the Merged Pack Child Backlog sheet. | [7 empty] | Portfolio Development Indicators
[8 empty] | Wave G conditional rows |  | Core management rows |  | P0 critical rows
[8 empty] | 6 |  | 44 |  | 33
[8 empty] | Packs at 0% |  | Highest pack readiness |  | Overall code-reality readiness
Pack | Capability Pack | Readiness | Current State | Critical Blocker | Next Gate | Primary Owner |  | 4 |  | 55% |  | 14%
1 | Project Route & Planner Configuration | 0% | Not started | Product Master, PPM, country requirements and rules engine are absent. | Build Wave B/C foundations and product planner. | PPM / Product Master
2 | Finite Project | 0% | Not started | MOD-0117 PPM is absent. | Implement finite-project MVP after product identity. | PPM
3 | Development & Technology Transfer | 0% | Planning scope | Stage planning can be developed; manufacturing, batch, capacity, equipment, procurement and QC execution remain external integrations. | Implement S0–S9 stage planning and external-execution dependency model. | R&D–RA / PPM
4 | Stage-Gate Decision | 10% | Infrastructure only | Workflow is partial; PPM stage-gate and rules engine are absent. | Activate workflow and implement PPM/rules stage-gate slice. | PPM / Workflow
5 | Source-Document Requirement Engine | 8% | Backbone fragments only | Documents are partial, but dossier, rules, evidence linking and Pack 5 runtime are absent. | Complete Waves A+B+C before Pack 5 runtime. | Evidence / RIM
6 | Work Package / Task / Process Instance | 22% | Partial backbone only | Workflow/scheduler/notifications are partial; persistent task backend is only 12%. | Build task engine and integrate workflow, scheduler and notifications. | Task / Workflow
7 | Controlled Source-Document Version | 55% | Partial — blocked | Document stack is ~80%, but approval integration, records and full e-signature controls are incomplete. | Close MOD-0029×0023, retention and cold-start proof. | Document Control
8 | CTD Readiness & RA Tasks | 5% | Not started | Dossier, rules and evidence linking are absent; task engine is only a mock. | Complete backbone, then implement CTD readiness. | RA / RIM
9 | CTD Section & Dossier Version | 0% | Not started | Dossier, market requirements, labeling and variations are absent. | Implement Wave E regulatory domain foundation. | RA / RIM
10 | Lifecycle Trigger & Work Order | 5% | Not started | Obligations, variations, task engine and MOD-0204 stability lifecycle runtime are absent. | Implement Wave F obligations, variations, stability and trigger-to-work-order flows. | RA / Stability / Compliance
Consolidation rule: rows are merged only when they share the same canonical Primary Module, system-of-record boundary and completion gate. The merged management row does not merge underlying object ownership. Pack-level acceptance criteria, interfaces, failure paths and tests remain separate child backlog items.
Seq | Wave | Layer | Primary Module | Related Modules | Capability / Development Part | Required Development Scope | Packs | Priority | Scope Class | Readiness | Confidence | Evidence / Data Quality Note | Completion / Dependency Gate | Code-Reality Status
1 | Wave 0 | Architecture Governance | Governance Artifact | All block modules | Capability and SoR baseline — Master 8.1 | Approve object ownership, pack-to-module mapping, Master 8.1 canonical identities, boundaries, manual alternatives and release scope. | 1–10 | P0 Critical | Governance Artifact | 10% | High | Capability matrix exists as workbook content; owner approval remains. | Approve DLE-SW-CAP-001 before module-pack development. | GOVERNANCE ONLY
2 | Wave 0 | Integration Governance | Interface Registry | All cross-module dependencies | API/Event contract baseline — Master 8.1 | Approve commands, queries, events, payload versions, authorization, idempotency, retries and failure behavior. | 1–10 | P0 Critical | Governance Artifact / Shared Platform | 40% | High | Interface Registry runtime partly exists; versioned payload contracts remain incomplete. | Publish approved v1 interface contracts. | PARTIAL
3 | Wave 0 | Decision Governance | MOD-0007 | MOD-0021; MOD-0028; MOD-0031; MOD-0357 | Decision & Rationale Log | Provide authoritative decision records, rationale, alternatives, consequences and decision-to-evidence links for stage gates, dossier decisions and lifecycle exceptions. | 1–10 | P0 Critical | Shared Governance Dependency | 0% | Low | Master 8.1 canonical module; not covered by the 26 July repository audit. | Decision records are versioned, evidence-linked and queryable from project, gate, dossier and lifecycle objects. | NOT ASSESSED
4 | Wave 0 | Security | MOD-0018 | All modules | RBAC / ABAC Authorization | Implement product-, project-, task-, document-, dossier- and market-scoped permissions with tenant isolation. | 1–10 | P0 Critical | Shared Platform Dependency | 62% | High | Platform authorization exists; DLE scopes and claim wiring are incomplete. | Server-side positive, negative and cross-tenant tests pass. | PARTIAL
5 | Wave 0 | Audit | MOD-0021 | All modules | Audit Trail Service | Record plan, task, approval, document, gate, dossier, submission and lifecycle state changes. | 1–10 | P0 Critical | Shared Platform Dependency | 55% | High | Audit runtime exists; DLE event taxonomy and object bindings are missing. | Every regulated mutation emits queryable audit evidence. | PARTIAL
6 | Wave 0 | Reference Data | MOD-0048 | MOD-0117; MOD-0236; MOD-0239 | Reference Data Management | Govern routes, stages, gates, legal bases, markets, statuses, dossier types and lifecycle triggers. | 1–10 | P0 Critical | Shared Platform Dependency | 68% | High | Reference-data APIs exist; DLE-specific values and effective-dated bindings are missing. | DLE catalogues are seeded, approved and API-accessible. | PARTIAL
7 | Wave 0 | Electronic Approval | MOD-0022 | MOD-0023; MOD-0029; MOD-0206; MOD-0117; MOD-0236; MOD-0358 | e-Signature Service | Bind identity, intent, meaning, timestamp and signed object version to approvals. | 4, 7, 9 | P0 Critical | Shared Platform Dependency | 45% | High | Document-level signature capability exists; gate and dossier bindings are absent. | Gate, document and dossier signature golden flows pass. | PARTIAL
8 | Wave 0 | Authority Governance | MOD-0358 | MOD-0018; MOD-0022; MOD-0023; MOD-0288 | Delegated Authority & Approval Limits | Govern authority policies, approval limits, grants, mandates, temporary authority instruments, exceptions and revocations used by project, gate, dossier and lifecycle approvals. | 2, 4, 7, 8, 9, 10 | P0 Critical | Shared Management & Governance Dependency | 0% | Low | New Master 8.1 canonical module; no repository readiness evidence was supplied. | Approval eligibility and limits are queryable and enforced by workflow without duplicating identity or workflow ownership. | NOT ASSESSED
9 | Wave 0 | Governance Structure | MOD-0359 | MOD-0357; MOD-0023; MOD-0029; MOD-0220; MOD-0288 | Governance Bodies, Charters & Accountability Registry | Govern persistent review boards, steering committees, charter versions, mandates, membership terms, decision rights and accountability matrices. | 1–4, 8–10 | P1 High | Shared Management & Governance Dependency | 0% | Low | New Master 8.1 canonical module; no repository readiness evidence was supplied. | Governance bodies and accountability are queryable without duplicating review instances, controlled documents or legal-entity records. | NOT ASSESSED
10 | Wave 0 | Records Governance | MOD-0030 | MOD-0029; MOD-0236 | Records Management (Retention/Legal Hold) | Implement retention classes, legal hold, disposition, archive retrieval and submission-record governance. | 7, 9, 10 | P0 Critical | Shared Platform Dependency | 18% | High | Document/audit retention exists partially; legal hold and submission archive are absent. | Regulated-record lifecycle and archive retrieval pass. | PARTIAL
11 | Wave 0 | Resilience | MOD-0044 | All persisted modules | Backup & Restore | Validate recovery of projects, tasks, documents, dossiers, audit and lifecycle records. | 1–10 | P1 High | Shared Platform Dependency | 5% | High | No regulated restore-validation runtime was found. | Restore and recovery-evidence test passes. | NOT STARTED
12 | Wave 0 | Metadata Governance | MOD-0052 | MOD-0290; MOD-0028; MOD-0236 | Metadata Catalog | Govern definitions, ownership, lineage and controlled discovery. | 5, 7, 8, 9 | P1 High | Shared Data-Governance Dependency | 5% | High | Existing module catalogue is not an R&D–RA metadata catalogue. | Metadata ownership and lineage become queryable. | NOT STARTED
13 | Wave A | Workflow | MOD-0023 | MOD-0117; MOD-0024; MOD-0029; MOD-0236 | Workflow Designer (Approvals/SLAs/Escalations) | Complete templates, versions, instances, approvals, transitions, permissions and runtime smoke tests. | 4, 6, 7, 8, 9 | P0 Critical | Shared Platform Dependency | 58% | High | Workflow features and gateway routes exist; complete runtime evidence is missing. | Workflow golden flow and failure paths pass. | PARTIAL
14 | Wave A | Document/Evidence | MOD-0028 | MOD-0029; MOD-0031 | Documentation & Evidence Management | Stabilize persistence, metadata, language, tenant isolation, queries and evidence registration. | 5, 7, 8, 9 | P0 Critical | Shared Platform Dependency | 80% | High | Broad runtime exists; remaining list/language failures must be closed. | Runtime failures resolved and regression suite passes. | PARTIAL
15 | Wave A | Controlled Documents | MOD-0029 | MOD-0028; MOD-0023; MOD-0022; MOD-0030 | Controlled Documents (SOPs/Work Instructions) | Stabilize SOP/work-instruction controlled states, approvals and training linkages; MOD-0029 does not own all controlled quality source documents. | 7, 9 | P0 Critical | Shared Platform Dependency | 80% | High | Major document functions exist; workflow integration and cold-start proof are incomplete. | Controlled-document lifecycle passes at L3 persistence. | PARTIAL
16 | Wave A | Quality Document Control | MOD-0206 | MOD-0028; MOD-0029; MOD-0023; MOD-0022; MOD-0021; MOD-0030; MOD-0031 | Controlled Quality Document Lifecycle and Pack 7 Runtime | Implement controlled quality-document semantics for protocols, specifications, reports and other GxP/QMS source documents; create deliverables from tasks; manage version, review, approval, electronic signature, effective state, expiry, supersession and retention; link evidence, CTD/dossier references and budget/effort references. | 4, 5, 7, 8, 9 | P0 Critical | QMS Dependency / R&D–RA Vertical Slice | 0% | High | MOD-0206 dedicated runtime is not started. Supporting MOD-0028/MOD-0029 document capabilities are partial, but workflow integration, QMS ownership, retention and end-to-end approval remain incomplete. | Task-to-approved-quality-document golden flow, version lifecycle, signature, evidence links, retention, idempotency, tenant isolation and L3 persistence pass. | BLOCKED
17 | Wave A | Scheduling | MOD-0026 | MOD-0024; MOD-0219; MOD-0204; MOD-0357 | Scheduler / Job Orchestration | Implement job management, retry, cancel, history, monitoring, deduplication and failure visibility. | 6, 10 | P1 High | Shared Platform Dependency | 52% | High | Background-job infrastructure exists; operational controls and DLE triggers are incomplete. | Scheduler operational and failure-path tests pass. | PARTIAL
18 | Wave A | Notifications | MOD-0027 | MOD-0023; MOD-0024; MOD-0026 | Notification Service (Email/SMS/WhatsApp) | Implement assignment, approval, overdue, reminder, delivery, retry and escalation behavior. | 4–10 | P0 Critical | Shared Platform Dependency | 50% | High | Notification runtime exists but uses a fake provider; real delivery is missing. | Real delivery channel and overdue escalation pass. | PARTIAL
19 | Wave B | Task Backbone | MOD-0024 | MOD-0023; MOD-0026; MOD-0027 | Task & Checklist Engine | Implement work package, task, checklist, work order, dependencies, assignment, status, effort and closure evidence. | 4, 5, 6, 8, 10 | P0 Critical | Shared Platform Dependency | 12% | High | Only an in-memory frontend mock exists; no persistent backend engine. | Persistent L3 task runtime, RBAC, audit and tenant tests pass. | PARTIAL
20 | Wave B | Rules Backbone | MOD-0025 | MOD-0117; MOD-0236; MOD-0219 | Business Rules Engine | Implement versioned rules, effective dates, evaluation, simulation, explanation and publication. | 1, 4, 5, 8, 10 | P0 Critical | Shared Platform Dependency | 0% | High | No rules-engine implementation was found. | Applicability, readiness and trigger rule families pass. | NOT STARTED
21 | Wave B | Evidence Backbone | MOD-0031 | MOD-0028; MOD-0029; MOD-0236 | Evidence Linking Service (object ↔ evidence) | Implement version-specific requirement, task, document, shared-scope and CTD links with coverage queries. | 5, 7, 8, 9 | P0 Critical | Shared Platform Dependency | 0% | Medium | Repository audit found no implementation; prior readiness values conflict. | Reinspection confirms baseline, then full linking runtime passes. | NOT STARTED
22 | Wave B | Shared Evidence | Composite Capability | MOD-0028; MOD-0031; MOD-0025; MOD-0140; MOD-0220; MOD-0290 | Shared Evidence Management | Implement reusable substance, site, supplier, material and legal-entity evidence with adoption and impact propagation. | 5, 7, 8, 9, 10 | P0 Critical | Composite R&D–RA Capability | 8% | Medium | Document services exist, but shared-scope resolution and adoption do not. | Shared-evidence ownership and resolution APIs pass. | BLOCKED
23 | Wave C | Product Master Integration | MOD-0290 | MOD-0140; MOD-0220; relevant MDM modules | Product / Item / SKU Master Integration | Supply product, strength, dosage form, route, pack and master-scope references. | 1–10 | P0 Critical | External Master Dependency | 0% | High | No Product/SKU Master runtime was found. | Valid Product Presentation query is available to R&D–RA. | NOT STARTED
24 | Wave C | Product Lifecycle | Composite Capability | MOD-0290; MOD-0117; MOD-0236; MOD-0237; MOD-0219 | Product Lifecycle Record | Implement permanent product lifecycle context linking projects, dossiers, registrations, obligations and decisions. | 1–10 | P0 Critical | Composite R&D–RA Capability | 0% | High | No canonical lifecycle-record runtime exists. | SoR approved and lifecycle record survives project closure. | NOT STARTED
25 | Wave C | Work Structuring | MOD-0354 | MOD-0117; MOD-0024; MOD-0023; MOD-0031 | Decomposition & Work Structuring Engine | Provide reusable structure definitions, node definitions, hierarchy rules, templates, instances, nodes, structural dependencies and baseline snapshots for project, stage, dossier and lifecycle work structures. | 1, 2, 3, 5, 6, 8, 9, 10 | P0 Critical | Shared Management & Governance Dependency | 0% | Low | New Master 8.1 canonical module; no repository readiness evidence was supplied. | Structural mechanics are reusable while project ownership remains MOD-0117, tasks remain MOD-0024 and workflows remain MOD-0023. | NOT ASSESSED
26 | Wave C | Business Process Governance | MOD-0355 | MOD-0354; MOD-0023; MOD-0024; MOD-0029; MOD-0288 | Business Process Architecture & Modeling | Govern process architectures, domains, families, processes, models, versions, activities, control points, role bindings and KPI bindings used by product development and RA operating processes. | 1–10 | P0 Critical | Shared Management & Governance Dependency | 0% | Low | New Master 8.1 canonical module; no repository readiness evidence was supplied. | Process definitions and versions are governed; workflow runs remain MOD-0023-owned and operational tasks remain MOD-0024-owned. | NOT ASSESSED
27 | Wave C | Product Planning & Project Management | MOD-0117 | MOD-0290; MOD-0239; MOD-0354; MOD-0355; MOD-0357; MOD-0023; MOD-0024; MOD-0025; MOD-0022; MOD-0206; MOD-0007; MOD-0358; MOD-0359; MOD-0136; MOD-0137; MOD-0291 | Product Planning, Finite Project, Development Stages and Stage-Gate Management | Implement product route, target markets, legal basis and planning assumptions; create an approved Product Plan Baseline; manage finite-project charter, WBS, schedule, milestones, risks, budgets and forecasts; instantiate S0–S9 development/TT stages with entry/exit criteria and work packages; execute stage-gate readiness, review and approve/condition/hold/rework/stop decisions; close projects and hand over to the Product Lifecycle Record. | 1, 2, 3, 4 | P0 Critical | Core R&D–RA Domain | 0% | High | No PPM/product-planner, finite-project, Development/TT stage or stage-gate runtime exists. Workflow and document dependencies are only partially implemented. | Product plan baseline, finite project, S0–S9 stage plan, gate decision, budget/forecast references, audit, evidence, reload persistence and project closure golden flows pass. | NOT STARTED
28 | Wave C | Management Review | MOD-0357 | MOD-0359; MOD-0007; MOD-0023; MOD-0024; MOD-0028 | Management Review & Cadence | Govern recurring stage-gate, portfolio, dossier and lifecycle review cycles, instances, agendas, review packs, attendance, outcomes and cadence configurations. | 2, 4, 8, 9, 10 | P1 High | Shared Management & Governance Dependency | 0% | Low | New Master 8.1 canonical module; no repository readiness evidence was supplied. | Review instances and outcomes are governed without taking ownership of bodies, decisions, tasks, reports or evidence. | NOT ASSESSED
29 | Wave C | R&D–RA Work Execution | Composite Capability | MOD-0354; MOD-0355; MOD-0117; MOD-0024; MOD-0023; MOD-0026; MOD-0027 | Pack 6 — Work Package, Task and Process Instance | Implement product/project/stage-aware tasks, process instances, schedules, assignments, completion evidence and folders. | 6 | P0 Critical | Composite R&D–RA Capability | 5% | Medium | Shared workflow exists partially; task backend and PPM context are absent. | Product task executes, persists, completes and links evidence. | BLOCKED
30 | Wave C | Project Financial Integration | MOD-0136 | MOD-0137; MOD-0291; MOD-0117; MOD-0024 | Product, project, task and document budgeting | Implement cost objects, budget baseline, allocations, forecasts, commitments, actual references and variance visibility. | 1, 2, 3, 6, 7 | P0 Critical | External Finance Dependency | 0% | High | No R&D–RA budgeting or forecast integration runtime exists. | Budget and forecast contracts work without duplicating finance ownership. | NOT STARTED
31 | Wave C | Requirement Runtime | Composite Capability | MOD-0117; MOD-0290; MOD-0354; MOD-0355; MOD-0025; MOD-0024; MOD-0031; MOD-0028; MOD-0206 | Pack 5 — Source-Document Requirement Engine | Import and version the catalogue, evaluate applicability, resolve reuse, and generate evidence register, gaps, tasks, folders, budgets and gate bindings. | 5, 8 | P0 Critical | Composite R&D–RA Capability | 8% | Medium | Document services partially exist; product, planner, rules, task and linking foundations are missing. | Product-specific source-document tasks generate deterministically. | BLOCKED
32 | Wave E | Regulatory Master | MOD-0239 | MOD-0048; MOD-0117; MOD-0236 | Country and Market Requirements | Implement authority, procedure, legal basis, submission type, local requirements, language and effective dates. | 1, 8, 9 | P0 Critical | Core R&D–RA Domain | 0% | High | No country/market requirements runtime exists. | Effective market requirements drive planner and dossier behavior. | NOT STARTED
33 | Wave E | Regulatory Information & Submission Management | MOD-0236 | MOD-0239; MOD-0238; MOD-0237; MOD-0025; MOD-0031; MOD-0024; MOD-0206; MOD-0030; MOD-0007; MOD-0358; MOD-0359 | Regulatory Dossier, CTD Readiness, Submission and Authority Interaction Management | Implement dossier cycles and the CTD Module 1–5 hierarchy with 58 section instances; map evidence to sections; calculate readiness, missing/expired evidence and exceptions; generate RA authoring/review/approval tasks; manage section and dossier versions, core/regional variants, quality gates, approval, lock and manifests; manage authority questions and deficiency-response work packages; package submissions and retain immutable submission, receipt and correspondence records. | 5, 8, 9, 10 | P0 Critical | Core R&D–RA Domain | 0% | High | No Dossier/RIM, CTD-section, readiness, authority-response or locked-submission runtime exists. Rules, evidence linking and task dependencies are also incomplete. | Dossier cycle, 58-section readiness, RA tasks, section/dossier versions, approval authority, submission package, authority-response and immutable archive golden flows pass. | BLOCKED
34 | Wave E | Labeling | MOD-0238 | MOD-0236; MOD-0237; MOD-0239 | Labeling Lifecycle | Implement core and regional product-information versions, SmPC/PIL/label approval and market status. | 9, 10 | P0 Critical | Core R&D–RA Domain | 0% | High | No labeling lifecycle runtime exists. | Label version is linked to dossier, market and variation. | NOT STARTED
35 | Wave F | Regulatory Lifecycle | MOD-0237 | MOD-0236; MOD-0238; MOD-0239 | Variations and Renewals | Implement classification, affected products, markets and sections, evidence, dates, packages and authority correspondence. | 9, 10 | P0 Critical | Core R&D–RA Domain | 0% | High | No variations or renewals runtime exists. | Variation/renewal end-to-end flow passes. | NOT STARTED
36 | Wave F | Obligations | MOD-0219 | MOD-0236; MOD-0237; MOD-0026; MOD-0027 | Obligations and Renewal Tracking | Implement obligation source, product/market scope, owner, due date, recurrence, evidence, escalation and fulfilment. | 10 | P0 Critical | Core R&D–RA Domain | 0% | High | No regulatory-obligation runtime exists. | Obligation generates due work and closes with evidence. | NOT STARTED
37 | Wave F | Lifecycle Automation | Composite Capability | MOD-0219; MOD-0237; MOD-0026; MOD-0024; MOD-0027; MOD-0204; MOD-0354; MOD-0355; MOD-0357 | Pack 10 — Lifecycle Trigger and Work Order | Implement expiry, review, commitment, renewal, variation and stability triggers that generate new work without reopening completed tasks. | 10 | P0 Critical | Composite R&D–RA Capability | 5% | Medium | Scheduler exists partially; obligation, variation, stability and persistent task contexts are absent. | Trigger deduplication, idempotency and work-order lineage pass. | BLOCKED
38 | Wave F | Stability Lifecycle | MOD-0204 | MOD-0219; MOD-0026; MOD-0024; MOD-0237; MOD-0236; MOD-0206 | Stability Planning and Lifecycle Integration | Implement stability plans, protocols, time points, due events, approved result references, overdue escalation, CTD evidence impact and lifecycle work-order generation. | 3, 5, 7, 8, 10 | P0 Critical | Mandatory Lifecycle Integration | 0% | High | No stability runtime exists; prior repository text matches were false positives. | Stability time points generate governed obligations, evidence impact and new work orders. | NOT STARTED
39 | Wave G | AI Governance | MOD-0068 |  | Prompt Registry and Approval Workflow | Version and approve prompts used for extraction, classification, drafting and review assistance; record owner, intended use and risk tier. | 5, 8, 9 | P1 High | Conditional AI Capability | 5% | High | A prompt-governance document exists, but no Prompt Registry runtime exists. | Activate only after an approved AI intended-use decision. | GOVERNANCE ONLY
40 | Wave G | AI Assurance | MOD-0069 |  | Human-in-the-Loop Verification | Implement reviewer assignment, verification, override, rejection, acceptance and evidence for AI/OCR outputs. | 5, 7, 8, 9 | P1 High | Conditional AI Capability | 0% | High | No Human-in-the-Loop verification runtime exists. | Activate with any approved AI/OCR production workflow. | NOT STARTED
41 | Wave G | AI Governance | MOD-0066 |  | Model Registry and Versioning | Record provider, model/version, approved use, validation evidence, deployment context and retirement state. | 5, 8, 9 | P1 High | Conditional AI Capability | 0% | High | No Model Registry implementation exists. | Activate before controlled production model use. | NOT STARTED
42 | Wave G | Agent Governance | MOD-0292 | MOD-0293 | Agent Registry and Execution Ledger | Register operational agents and persist run, step, checkpoint, trace, failure and human-approval history. | 5, 8, 9, 10 | P2 Later | Conditional AI Capability | 0% | High | No Agent Registry or execution-ledger implementation exists. | Required only when governed agents execute R&D–RA work. | NOT STARTED
43 | Wave G | Agent Tooling | MOD-0294 | MOD-0295 | Agent Tool Gateway and Operational Workspace | Control tool/API access and scopes; provide recommendations, pending approvals, run review and exception handling. | 5, 8, 9, 10 | P2 Later | Conditional AI Capability | 0% | High | No agent tool gateway or operational workspace exists. | Agents must use approved adapters and scopes. | NOT STARTED
44 | Wave G | AI Monitoring | MOD-0067 | MOD-0110 | Evaluation, Drift and AI Ethics Controls | Run regression and evaluation checks, monitor quality and drift, and govern ethical and responsible-use reviews. | 5, 8, 9 | P2 Later | Conditional AI Capability | 0% | High | No evaluation, drift or AI ethics runtime exists. | Activate after production AI scope is approved. | NOT STARTED
Build-Wave Summary | 0 | 0 | 0
Wave | 0 | 0 | 0 |  | Primary Outcome
Wave 0 | 12 | 12 | 9 | 25.67% | Approve Master 8.1 ownership, interfaces, decisions, authority, governance bodies and regulated controls.
Wave A | 6 | 6 | 5 | 53.33% | Stabilize workflow, document/evidence services and the consolidated MOD-0206 quality-document runtime.
Wave B | 4 | 4 | 4 | 5% | Build task, rules, evidence-linking and shared-evidence backbone.
Wave C | 9 | 9 | 8 | 1.444% | Deliver product context, work/process structures, consolidated MOD-0117 planning/project/stage/gate capability, reviews, tasks, budgets and Pack 5.
Wave E | 3 | 3 | 3 | 0% | Deliver country rules, consolidated MOD-0236 dossier/CTD/submission capability and labeling.
Wave F | 4 | 4 | 4 | 1.25% | Deliver variations, obligations, stability and lifecycle work orders.
Wave G | 6 | 6 | 0 | 0.8333% | Conditional AI and agent governance and runtime.
Integration X | 9 | 9 | 0 | 0.5556% | External study, manufacturing, capacity, Work Orders, Calibration, procurement, QC/LIMS and QMS change integrations.
5 | Permissions, tenant isolation and segregation of duties |  |  |  | Positive/negative authorization and cross-tenant tests | [5 empty] | Security | Yes
6 | Immutable audit events and correlation |  |  |  | Audit evidence for all critical regulated actions | [5 empty] | Compliance | Yes
7 | Frontend runtime flows, empty states and failure handling |  |  |  | Browser evidence for list/detail/create/edit/error states | [5 empty] | Frontend | Where UI applies
8 | Cross-module API and event contracts |  |  |  | Versioned contracts and consumer tests | [5 empty] | Integration | Yes
9 | Idempotency, retry, deduplication and concurrency |  |  |  | Duplicate/retry/concurrency test evidence | [5 empty] | Reliability | Yes
10 | Unit, integration, golden-flow and failure-path tests |  |  |  | Passing automated suites and runtime smoke reports | [5 empty] | QA | Yes
11 | Cold-start persistence, backup and restore verification |  |  |  | Restart, data retention and restore evidence | [5 empty] | Persistence | Yes
12 | Retention, e-signature and locked-version controls |  |  |  | Records, signature and package-lock evidence | [5 empty] | GxP | Where regulated
13 | Release, rollback, monitoring and operational evidence |  |  |  | Deployment, rollback, monitoring and release report | [5 empty] | Release | Yes
Unified Critical Path
Order | Critical Path Capability |  |  | Current State |  |  | Required Exit |  |  | Unlocks | Wave | Decision Type | Owner
1 | Master 8.1 reconciliation, SoR decisions, MOD-0007, MOD-0358 and MOD-0359 |  |  | Canonical plan updated; new modules not yet code-audited |  |  | Approved ownership, decision, authority and governance baseline |  |  | All packs | Wave 0 | Architecture | Enterprise Architecture
2 | RBAC, audit, records, reference data, metadata, backup and e-signature |  |  | Partially implemented or missing DLE bindings |  |  | Cross-cutting regulated controls runtime-proven |  |  | All packs | Wave 0 | Development | Platform / Compliance
3 | MOD-0023, MOD-0028, MOD-0029 and MOD-0206 |  |  | Shared document stack partial; QMS Document Control not started |  |  | Workflow active and task-to-approved-quality-document L3 flow |  |  | Packs 4–9 | Wave A | Development | Platform / QMS
4 | MOD-0024, MOD-0025, MOD-0031 and Shared Evidence |  |  | Missing, mocked or blocked |  |  | Persistent task, rules, evidence and reuse backbone |  |  | Packs 1,4,5,6,8,10 | Wave B | Development | Platform
5 | MOD-0290, MOD-0117, MOD-0354 and MOD-0355 |  |  | Product/PPM not started; M&G modules not assessed |  |  | Product identity, planning, work structures and process definitions |  |  | Packs 1–6 | Wave C | Development | MDM / PPM / M&G
6 | MOD-0357 plus projects, tasks and finance |  |  | Not started/not assessed |  |  | Review cadence, finite projects, gates, tasks, budgets and controlled evidence |  |  | Packs 2–7 | Wave C | Development | PPM / M&G / Finance
7 | MOD-0239, MOD-0236, MOD-0238 and MOD-0206 |  |  | Not implemented |  |  | Market requirements, CTD, dossier, labeling and submission foundation |  |  | Packs 5,8,9 | Wave E | Development | RA / RIM / QMS
8 | MOD-0237, MOD-0219, MOD-0204 and MOD-0357 |  |  | Not implemented/not assessed |  |  | Variations, obligations, stability, review cadence and lifecycle automation |  |  | Pack 10 | Wave F | Development | RA / Quality / M&G
9 | MOD-0199 Work Orders, MOD-0200 Calibration and other external contracts |  |  | Outside core; contracts absent |  |  | Versioned external contracts or controlled manual evidence modes |  |  | Packs 1–10 | Integration X | External Integration | Domain Owners

## AI Agent Platform Cap Block
Company-facing AI Interface + OpenAI Agent Layer — Capability Block
Target: Soft System company-facing Operational Agent Workspace backed by governed agent runtime, tool gateway, OpenAI API adapter, shared workflow/RBAC/audit, and GQMS document/knowledge services. OpenAI is an external intelligence provider, not a business-object SoR.
Planning Metric | Value |  | Architecture Control | Decision |  | Governance Control | Decision |  | Boundary | Rule
Consolidated sequences | 12 |  | Primary company-facing UI | MOD-0295 |  | Agent identity/lifecycle | MOD-0292 |  | Business SoR | Domain modules remain SoR; agent modules own only agent/workspace/runtime/policy artifacts.
Canonical core AI modules | 5 |  | OpenAI/API control point | MOD-0294 |  | Policy / guardrails | MOD-0296 |  | OpenAI | Provider/adapter behind MOD-0294; no browser-direct model calls and no direct unrestricted DB access.
New canonical MOD IDs required | 0 |  | Execution truth / ledger | MOD-0293 |  | Human approval | MOD-0069 + MOD-0023 |  | Controlled actions | MOD-0296 policy + MOD-0069 HITL + MOD-0023 workflow gate before state-changing execution.
Seq | Wave / Lane | Layer | Primary Module | Related / Reused Modules | Capability / Development Part | Required Development Scope | Primary Soft Pages / Surfaces | Dependency / Completion Gate | Minimum Integration Contracts | SoR / Boundary Rule | AI Risk | Priority | Current Readiness | Evidence / Data Quality Note | Completion / Release Gate | Runtime Vertical-Slice / Golden-Flow Requirement
1 | Wave 0 — Foundation | Identity / Security | MOD-0018 | MOD-0017; MOD-0020; MOD-0012; MOD-0021; MOD-0041 | Identity, authorization, SoD, secrets, audit and observability baseline | Enforce SSO identity, server-side RBAC/ABAC, SoD, secret isolation, immutable audit hooks, correlation IDs and redacted logging for every AI request/tool action. | Access policy view; audit trace; security exception view | SSO/MFA available; permission taxonomy approved; audit event contract and secrets handling frozen. | PLAT-BASE; AuditEvent v1; Correlation-ID; OTel; secrets hook | Identity/security modules remain authoritative. Agent modules consume user/role/tenant context and must not create a second permission system. | High | P0 Critical | Foundation reuse / hardening required | Existing platform capabilities are reused; production AI must not proceed until server-side permissions and audit are runtime-proven. | G0 — Security & Audit Baseline | Authenticated user invokes allowed read action; denied role gets server-side rejection; tenant isolation and audit/correlation evidence verified.
2 | Wave 0 — Foundation | Workflow / Work Management | MOD-0023 | MOD-0024; MOD-0025; MOD-0026; MOD-0027 | Workflow, tasks, rules, scheduling and notification mechanics | Provide approval checkpoints, reviewer tasks, remediation tasks, rule evaluation, scheduled sweeps and notification/escalation without duplicating workflow inside agent modules. | Approval queue; task/checklist; escalation state | Workflow golden flow and persistent task engine available; business-rule versioning approved. | WORKFLOW-BUNDLE; task/checklist contract; rules contract; notification event | MOD-0023 owns generic workflow; MOD-0024 owns task mechanics. Source/domain module retains business lifecycle semantics. | High | P0 Critical | Partial / requires runtime completion | Current project reports show workflow/scheduling pieces exist partially; persistent task/rules capabilities require completion. | G1 — Human Workflow Ready | Agent recommendation creates governed review task; reviewer approves/rejects; decision, evidence, SLA and audit persist at L3.
3 | Wave 0 — Foundation | Integration Backbone | MOD-0032 | MOD-0033; MOD-0034; MOD-0035; MOD-0041 | API gateway, credentials, webhooks/events and integration observability | Route browser traffic only through company backend/gateway; standardize service-to-service auth, quotas, retries, webhook/event patterns and correlation propagation. | API Gateway Console; route/adapter health; retry/exception view | Gateway/auth contracts approved; no frontend direct calls to service ports or OpenAI. | API Gateway v1; OAuth/JWT service auth; Error Model; Correlation-ID; OTel | MOD-0032 owns interface routing. Domain APIs remain owned by domain modules. External AI calls are server-side only. | High | P0 Critical | Existing shared service / integrate | Blueprint already defines gateway and API-consumer management as shared platform capabilities. | G1 — Integration Boundary Ready | Frontend action → gateway → agent backend → approved tool/provider; trace visible end-to-end; failure returns controlled error with no orphan state.
4 | Wave 1 — AI Governance | Model / Prompt / HITL | MOD-0066 | MOD-0068; MOD-0069 | Model registry, prompt registry and human verification | Register provider/model/version/intended use; version and approve prompts; require reviewer assignment, verification, override/reject/accept evidence for controlled outputs. | Model Registry; Prompt Registry; HITL Review Queue | AI intended-use decision approved; model and prompt owners assigned; validation evidence available. | MODEL-REG; PROMPT-REG; HITL verification contract; AuditEvent v1 | These modules govern model/prompt/review artifacts; they do not own domain records created or assessed by AI. | High | P0 Critical | 0–5% / not runtime-ready | Current planning evidence indicates Prompt Registry ~5%; Model Registry and HITL runtime not implemented. | G2 — AI Intended Use Approved | Approved model + approved prompt executes a read/analysis task; output cannot affect controlled record until human verification is completed.
5 | Wave 1 — AI Assurance | Evaluation / Responsible AI | MOD-0067 | MOD-0110 | Evaluation, regression, drift and AI ethics controls | Define test sets, acceptance thresholds, regression runs, drift signals, failure escalation, bias/fairness review where applicable and retirement triggers. | Evaluation Dashboard; Drift Monitor; Ethics Review Panel | Model/prompt registry operational; representative evaluation dataset approved. | EVAL-BUNDLE; model-version reference; quality metric events; incident/escalation hooks | Evaluation owns AI-quality evidence only; business KPI truth remains in certified metric/domain modules. | Medium | P1 High | Not implemented / conditional | No evaluation/drift runtime evidence in current reports; required before production-scale agent operation. | G3 — AI Assurance Ready | Run pinned regression suite against approved model/prompt version; threshold breach blocks promotion and creates governed review/incident.
6 | Wave 1 — Agent Foundation | Agent Governance | MOD-0292 | MOD-0296; MOD-0066; MOD-0068; MOD-0069; MOD-0018 | Agent registry, lifecycle, owner/risk classification and action policy | Create governed AgentID/version/owner/risk/operating-mode/deployment-state registry plus allow/deny/escalate/approval thresholds and blocked-action policies. | Agent Registry Console; Agent Definition Detail; Policy Console; Guardrail Rule Builder | MOD-0066/0068/0069 and RBAC available; agent operating modes and risk taxonomy approved. | AGENT-REG-BUNDLE; AGENT-POLICY-BUNDLE; AI-RISK-BUNDLE; WORKFLOW-BUNDLE | MOD-0292 owns agent identity/lifecycle. MOD-0296 owns agent policy decisions. Neither owns domain business objects. | High | P0 Critical | 0% / canonical, not implemented | Master 8.1 explicitly defines both modules; current status evidence shows no production implementation. | G4 — Agent Governance Ready | Register versioned read-only GQMS agent; policy allows search/analyse, blocks approval/delete, and records every decision with actor/tenant/trace.
7 | Wave 2 — Agent Runtime | Execution Runtime | MOD-0293 | MOD-0292; MOD-0296; MOD-0069; MOD-0021; MOD-0041 | Agent orchestration runtime and execution ledger | Persist AgentRun, RunStep, checkpoints, runtime state, trace references, retries/failures and human approval checkpoint references. Support deterministic resumability and idempotency. | Run Detail; Execution Trace; Failure/Retry View | Agent registry and guardrail foundation stable; audit/observability contracts proven. | AGENT-RUNTIME-BUNDLE; AuditEvent v1; Correlation-ID; OTel | MOD-0293 is execution truth for agent runs; MOD-0021 remains immutable enterprise audit SoR. | High | P0 Critical | 0% / not implemented | Master 8.1 backlog says build after registry and guardrails are stable due to higher operational risk. | G5 — Runtime Ledger Ready | Start agent run → execute multiple governed steps → checkpoint → retry/resume → finish; complete trace persists at L3 with no duplicate side effects.
8 | Wave 2 — Agent Runtime | Tool / Provider Integration | MOD-0294 | MOD-0032; MOD-0033; MOD-0012; MOD-0296 | Agent Tool Gateway + OpenAI API adapter | Create controlled tool catalog, adapters, access scopes, invocation records, health monitoring and secrets hook. Implement OpenAI as an approved external intelligence-provider adapter behind this gateway. | Tool Catalog; Adapter Detail; Tool Scope Manager; Invocation Monitor; Provider Health | MOD-0296 policy enforcement and secrets/gateway foundation ready; approved OpenAI provider/security/DPA configuration exists. | AGENT-TOOL-BUNDLE; provider adapter contract; tool invocation request/response; Error Model; OTel | Tool gateway owns tool definitions/adapters/invocations only. OpenAI is not SoR. Domain modules remain authoritative and expose business functions, not raw unrestricted DB access. | High | P0 Critical | 0% / not implemented | Master 8.1 defines MOD-0294 specifically to prevent uncontrolled direct domain-system access. | G6 — Controlled Tooling Ready | Agent requests approved tool → policy validates scope → adapter invokes OpenAI/domain API → response recorded; forbidden tool is blocked; secret never reaches client/log.
9 | Wave 3 — Experience | Company-facing AI Work Center | MOD-0295 | MOD-0285; MOD-0286; MOD-0287; MOD-0288; MOD-0293; MOD-0296 | Operational Agent Workspace embedded in company Soft System | Build Agent Inbox, Recommendations, Pending Human Approvals, Exceptions, Run Review and Performance Dashboard using existing navigation, UI patterns, personalization and org/person routing. | Agent Inbox; Recommendations; Pending Approvals; Exceptions; Performance Dashboard | MOD-0293 runtime + MOD-0296 policy ready; navigation/UI/user preference/directory contracts stable. | AGENT-WORKSPACE-BUNDLE; NAV-RUNTIME; UI-GOV-BUNDLE; USER-PREF-BUNDLE | MOD-0295 owns workspace presentation artifacts only. Execution truth stays in MOD-0293; policy truth in MOD-0296; domain task/business truth stays with source modules. | Medium | P0 Critical | 0% / not implemented | Master 8.1 explicitly defines this as the unified business-facing workspace; experience layer follows runtime/governance foundations. | G7 — Company-facing Workspace Ready | User opens Work Center, submits governed AI task, sees progress/result, reviews evidence, approves/rejects where permitted, and can reopen run/audit trace after reload.
10 | Wave 3 — GQMS Enablement | Documents / Evidence / Repository | MOD-0028 | MOD-0029; MOD-0030; MOD-0031; MOD-0262 | Controlled GQMS document, record, evidence and binary repository services | Expose controlled document metadata/version/status, immutable record/retention rules, evidence links and repository access to agents through governed APIs. No agent-owned shadow document SoR. | Document search/detail; Evidence Viewer; Records/Retention view | Document/repository contracts runtime-proven; controlled write paths remain human-approved. | DOCS-BASE; DOC-REPO-BUNDLE; Evidence-Link; AuditEvent v1 | Controlled documents/records remain authoritative in existing modules. Derived AI index is disposable/rebuildable. | High | P0 Critical | Partial platform foundation | Existing document stack is the strongest foundation but requires approval/retention/evidence hardening for regulated operation. | G8 — GQMS Evidence Plane Ready | Read effective controlled document + version + evidence links; AI drafts proposal only; approved change uses governed workflow and preserves version/audit/retention.
11 | Wave 3 — Knowledge Enablement | Search / Metadata / Knowledge Graph | MOD-0056 | MOD-0052; MOD-0053; MOD-0057; MOD-0058; MOD-0040 | Enterprise retrieval, taxonomy and relationship/impact index | Index governed metadata and relationships for W2-style questions; support search, semantic tagging, entity linking and impact traversal while retaining source register/document authority. | Enterprise Search; Metadata Explorer; Relationship/Impact View | Canonical IDs/metadata taxonomy agreed; source adapters available; derived index rebuild process defined. | SEARCH contract; METADATA contract; TAXONOMY contract; KG/edge contract; Correlation-ID | Search/graph is a lens, not authority. If derived index conflicts with authoritative source, source wins and index is rebuilt. | Medium | P1 High | Foundation modules planned / mixed readiness | Blueprint contains all required knowledge-plane modules; implementation maturity must be audited before GQMS-wide indexing. | G9 — Governed Retrieval Ready | Question resolves canonical object → traverses approved relationships → returns affected codes/paths with source/version provenance; unresolved edges are stated explicitly.
12 | Wave 4 — GQMS Agent Services | Domain Agent Service Pack | Composite — no new MOD | MOD-0292–0296; MOD-0023–0031; MOD-0052–0058; MOD-0066–0069 | GQMS Orchestrator + W1 Sweep + W2 Question + W3 Controlled Change | Register GQMS specialist agents; expose W1 deterministic conformance sweep, W2 impact/dependency queries and W3 proposal→review→approval→controlled execution. Keep deterministic checks outside LLM prompts where possible. | GQMS AI Task; Sweep Findings; Impact Result; Change Proposal; Execution Evidence | G0–G9 gates complete for intended scope; GQMS URS/validation strategy and permission profile approved. | GQMS-SERVICE contracts over AGENT-TOOL/RUNTIME/WORKSPACE/POLICY bundles | No new business SoR. W1/W2 derived outputs are working evidence; W3 may execute only exact approved actions through deterministic services. | High | P0 Critical | Design-defined / implementation pending | The existing GQMS workflow note already defines W1/W2/W3 boundaries; this sequence operationalizes them through the canonical agent platform modules. | G10 — GQMS AI Operational Release | End-to-end: user launches W1/W2 from company Work Center; recommendation becomes governed task; human approves W3 proposal; executor performs hash/audit-verified action; post-change sweep proves result.
Capability Block Governance Notes
Decision | Do not create a new ChatGPT/AI Work Center module. MOD-0295 is the company-facing Operational Agent Workspace.
Decision | Do not expose OpenAI directly to browser, database, or uncontrolled file system. OpenAI integration is a provider adapter/tool path under MOD-0294.
Decision | MOD-0292–0296 own only agent definitions, runs, tools, workspace artifacts and policy decisions. Domain modules remain SoR for business objects.
Mandatory runtime rule | All state-changing screens and actions follow the Runtime Vertical-Slice rules: real persistence, server-side RBAC, tenant isolation, audit, concurrency, idempotency and failure-path validation.
Build governance | Because this is cross-cutting/multi-module work, prepare a Delivery Capability Pack first, then approved/ready-for-dev module packs before coding.
Release recommendation | Phase 1 should be read/analyse/draft only. Activate controlled execution only after policy/HITL/runtime/tool-gateway evidence is validated.

## Supply Planning Procure Cap Blo
Supply Planning, Procurement, Inventory, Warehouse & BOM — Capability Block
Target operating chain: Product/Item/SKU → Inventory truth → Procurement core + BOM foundation (parallel lanes) → Demand/MRP/Safety Stock → Warehouse execution → Integrated S&OP/Capacity/Logistics. Domain ownership remains single-SoR; planning modules propose requirements while purchasing/inventory/warehouse modules execute transactions.
Planning Metric | Value |  | Sequence Control | Decision |  | Ownership Control | Decision |  | Architecture Boundary | Rule
MVP count | 6 |  | Foundation | MVP-1 |  | Product master SoR | MOD-0290 |  | MRP | Creates/plans replenishment/material requirements; does not own purchase orders.
Primary critical-spine modules | 9 |  | Parallel lane A | MVP-2 Procurement |  | Inventory SoR | MOD-0173 |  | Warehouse | Executes putaway/pick/pack/count; does not create a second inventory ledger.
Parallel lanes after MVP-1 | 2 |  | Parallel lane B | MVP-3 BOM |  | Purchase transaction SoR | MOD-0141 |  | BOM | Defines manufacturing material/routing structure; product/item identity remains MOD-0290.
New canonical module IDs | 0 |  | Planning convergence | MVP-4 Demand + MRP |  | BOM/routing SoR | MOD-0193 |  | S&OP | Governed integration of demand, supply, capacity and inventory plans; source operational records stay in their owning modules.
Seq | MVP | Wave / Lane | Primary Module(s) | Related / Supporting Modules | Capability / Development Part | Required Development Scope | Primary Business Golden Flow | Dependency / Completion Gate | Key Interfaces / Events | SoR / Boundary Rule | Priority | Readiness / Status | Evidence / Data Quality Note | Exit Gate | Parallelization / Sequencing Note | Runtime Vertical-Slice Requirement | Release Outcome
1 | MVP-1 | Foundation | MOD-0290; MOD-0173; MOD-0174; MOD-0175; MOD-0176; MOD-0177 | MOD-0040; MOD-0048; MOD-0018; MOD-0021; MOD-0031 | Product + Inventory Foundation | Establish canonical product/item/SKU/UoM identity and authoritative inventory balance/valuation with lot-batch-serial traceability, quarantine/blocked stock, expiry/FEFO and recall-readiness controls. | Create/consume product item → receive opening/initial stock → assign lot/batch/serial → place available/quarantine status → query authoritative stock position and trace. | Canonical IDs, reference data, RBAC, audit and evidence contracts ready. No downstream MVP may create competing product or inventory truth. | PRODUCT-MASTER-BUNDLE; inventory ledger API/events; lot trace event; stock-status event; evidence link | MOD-0290 owns product/item/SKU reference master. MOD-0173 owns stock balance/valuation. MOD-0174–0177 own traceability/status policies, not duplicate balances. | P0 Critical | Foundation / first release | This is the dependency anchor for purchasing, MRP, warehouse and BOM. Treat data quality and canonical identity as stop-ship gates. | G1 — Product & Inventory Truth Ready | Must complete before MVP-2/3. After contracts stabilize, procurement and BOM can develop in parallel. | Real create/read/update flows, L3 persistence for inventory/traceability, server-side RBAC/tenant isolation, audit, concurrency and idempotent stock movements. | Reliable product and stock truth
2 | MVP-2 | Parallel Lane A after MVP-1 | MOD-0140; MOD-0141; MOD-0142; MOD-0143; MOD-0145 | MOD-0144; MOD-0023; MOD-0024; MOD-0021; MOD-0290; MOD-0173 | Procurement / Purchasing Core | Deliver supplier onboarding, sourcing/RFQ, requisition and purchase order lifecycle, receiving/GRN and invoice capture/3-way match. Include contract linkage where required without making contract management a blocker for the thin core. | Supplier approved → source/select supplier → create requisition → approval → issue PO → receive/GRN → inventory updated → invoice matched against PO/GRN. | MVP-1 product/inventory contracts ready; supplier, workflow, audit and purchasing permissions approved. | Supplier reference; requisition/PO API; approval events; GRN event; inventory receipt event; invoice-match contract | MOD-0141 owns requisition/PO transaction. MOD-0142 owns receipt/GRN. MOD-0143 owns invoice matching. Inventory posting updates MOD-0173; procurement must not maintain shadow stock. | P0 Critical | Core P2P MVP | MOD-0144 Contracting can be a controlled extension; MOD-0147/0148 are intentionally deferred to MVP-6. | G2A — Procure-to-Receive Ready | Can run in parallel with MVP-3 once MVP-1 contracts freeze. | End-to-end requisition→PO→GRN→inventory→invoice-match golden flow with L3 persistence, approval/audit, failure rollback and duplicate-submit protection. | Operational procure-to-receive / P2P
3 | MVP-3 | Parallel Lane B after MVP-1 | MOD-0193 | MOD-0290; MOD-0209; MOD-0040; MOD-0003 | BOM & Routings Foundation | Create governed BOM versions, component lines, quantities/UoM, effective dates, alternate/substitute relationships where approved, routing steps and controlled change linkage. Keep the MVP thin enough to unblock dependent-demand planning. | Select product/item → create BOM version → add components/routing → validate references/UoM → approve/effect version → query current effective structure. | MVP-1 item/SKU master stable; BOM ownership and change-control contract approved. | BOM schema/API; BOM-version event; component requirement contract; change-control reference | MOD-0193 owns BOM/routing structures. MOD-0290 remains item/product identity SoR. Change-control lifecycle is consumed rather than duplicated. | P0 Critical | Foundation for manufacturing-grade MRP | If the business is distribution-only, this MVP can be deferred; for manufacturing/pharma it should precede full MRP. | G2B — BOM Structure Ready | Runs parallel with MVP-2. Both MVP-2 and MVP-3 feed MVP-4. | Versioned BOM/routing records persist at L3, optimistic concurrency on revisions, controlled effective-state transition, audit/evidence on change. | Governed material structure
4 | MVP-4 | Planning Convergence | MOD-0188; MOD-0189; MOD-0191 | MOD-0290; MOD-0173; MOD-0193; MOD-0141; MOD-0142 | Demand + MRP / Replenishment | Implement demand plans/forecasts, MRP/net requirements, replenishment proposals and safety-stock policies. Consume current inventory, open supply, lead times and BOM-dependent demand where applicable. | Forecast demand → explode BOM if manufacturing → net against inventory/open supply → apply safety stock/lead time → calculate requirement → create replenishment/purchase proposal → hand off approved requirement to MOD-0141. | G2A Procurement and G2B BOM ready for relevant scope; inventory snapshots and planning parameters reliable. | Demand-plan contract; inventory availability query; open-PO/supply query; BOM explosion contract; replenishment proposal event; purchase-requisition handoff | MOD-0188 owns demand plan. MOD-0189 owns planning calculations/proposals, not POs. MOD-0191 owns safety-stock policy/optimization. MOD-0141 remains purchase transaction SoR. | P0 Critical | Planning MVP | MRP quality depends on inventory accuracy, lead-time data and BOM completeness. Flag degraded-mode planning if any source is incomplete. | G3 — Replenishment Planning Ready | Begins after both parallel lanes are sufficiently stable; warehouse execution is not a hard prerequisite. | Forecast/planning save-reload, reproducible calculation snapshot, explainable netting inputs, idempotent proposal generation, approval/audit for release to purchasing. | Forecast-to-replenishment operational planning
5 | MVP-5 | Warehouse Execution | MOD-0178; MOD-0180; MOD-0181; MOD-0182 | MOD-0179; MOD-0173; MOD-0174; MOD-0142; MOD-0035 | Warehouse Operations | Deliver putaway, bin/location execution, picking, packing, wave planning, cycle counting and barcode/RFID support. Treat 3PL integration as conditional unless required for launch. | GRN/inventory receipt → putaway → locate stock → release pick/wave → pick → pack → confirm movement → cycle count/adjust under governed controls. | MVP-1 inventory/lot contracts stable; receiving event available; warehouse location model and permissions approved. | GRN-to-putaway event; inventory movement API/event; pick/pack contract; count adjustment contract; barcode scan contract | Warehouse modules own physical execution instructions/status. MOD-0173 remains authoritative inventory ledger; every warehouse movement posts through governed inventory contract. | P0 Critical | Execution MVP | Can start detailed design in parallel with late MVP-4; production go-live depends on stable inventory transaction semantics. | G4 — Warehouse Execution Ready | Does not have to block MVP-4. Can be developed after MVP-1 while procurement/MRP mature, but integration smoke must use real inventory postings. | Putaway/pick/pack/count golden flows with per-row/server authorization, idempotent scans/movements, concurrency handling, partial-failure markers for bulk/wave actions. | Controlled physical warehouse execution
6 | MVP-6 | Integrated Planning + Logistics | MOD-0190; MOD-0192; MOD-0183; MOD-0184; MOD-0185; MOD-0186; MOD-0187 | MOD-0147; MOD-0148; MOD-0188; MOD-0189; MOD-0173; MOD-0178; MOD-0193 | Integrated S&OP, Capacity, Supplier Performance & Downstream Logistics | Add governed S&OP workflow/sign-offs, capacity planning, carrier/routing/load planning, shipment tracking/POD, reverse logistics and claims. Add supplier performance/risk and supplier portal after core purchasing stabilizes. | Demand/supply plan → capacity review → S&OP approval → supply/execution plan → warehouse shipment → carrier/load → POD → exception/return/claim; supplier performance feedback closes the loop. | MVP-2 through MVP-5 production contracts stable; planning and logistics ownership approved; KPI/metrics and workflow controls available. | S&OP approval events; capacity plan contract; shipment/carrier/load contracts; POD event; return/claim contracts; supplier performance events | MOD-0190 governs integrated planning workflow, not source demand/inventory/PO records. MOD-0192 owns capacity plans. Logistics modules own shipment/transport lifecycle; procurement modules retain supplier/PO truth. | P1 High | Advanced integrated release | This is intentionally last because it integrates multiple proven operational SoRs and requires stronger analytics/exception handling. | G5 — Integrated Supply Chain Ready | Starts only after core source systems have stable contracts; selected logistics pieces may be parallelized if external integration readiness permits. | Cross-module golden flow with versioned plan snapshots, approval/audit, correlation IDs across shipment lifecycle, controlled exceptions and reconciliation to source SoRs. | Integrated supply-chain planning and logistics
Canonical Module Roster by Capability
Capability Area | Module | Canonical Role | MVP | Core / Supporting | Boundary / Notes
Product Master | MOD-0290 | Product / Item / SKU Master | MVP-1 | Core | Canonical product/item/SKU/UoM registry.
Inventory | MOD-0173 | Inventory Ledger & Valuation | MVP-1 | Core | Authoritative inventory balance/value SoR.
Inventory | MOD-0174 | Lot / Batch / Serial Tracking | MVP-1 | Core | Traceability identity/status linked to inventory.
Inventory | MOD-0175 | Quarantine / Blocked Stock | MVP-1 | Core | Quality/availability status; no duplicate balance.
Inventory | MOD-0176 | Expiry / FEFO Management | MVP-1 | Core | Expiry/FEFO policy.
Inventory | MOD-0177 | Recall Readiness | MVP-1 | Supporting | Recall/trace readiness.
Procurement | MOD-0140 | Supplier Onboarding | MVP-2 | Core | Supplier readiness/master workflow.
Procurement | MOD-0145 | Sourcing (RFQ/RFP) | MVP-2 | Core | Source/select supplier.
Purchasing | MOD-0141 | Requisition & Purchase Orders | MVP-2 | Core | Purchasing transaction SoR.
Procurement | MOD-0142 | Receiving / GRN | MVP-2 | Core | Receipt/GRN SoR; posts to inventory.
Procurement | MOD-0143 | Invoice Capture & 3-Way Match | MVP-2 | Core | PO/GRN/invoice matching.
Supplier Controls | MOD-0144 | Contracting & Clause Library | MVP-2 | Supporting | Contract linkage/control; can be phased.
BOM | MOD-0193 | BOM & Routings | MVP-3 | Core | Manufacturing material/routing structure.
Forecasting | MOD-0188 | Demand Planning | MVP-4 | Core | Operational demand plan/forecast SoR.
MRP | MOD-0189 | MRP & Replenishment | MVP-4 | Core | Net requirements and replenishment proposals.
Planning | MOD-0191 | Safety Stock Optimization | MVP-4 | Core | Safety-stock policy/optimization.
Warehouse | MOD-0178 | Putaway / Picking / Packing | MVP-5 | Core | Warehouse execution.
Warehouse | MOD-0180 | Wave Planning | MVP-5 | Core | Wave/workload execution planning.
Warehouse | MOD-0181 | Cycle Counting | MVP-5 | Core | Physical count and governed adjustment.
Warehouse | MOD-0182 | Barcode / RFID | MVP-5 | Core | Execution/scanning support.
Warehouse | MOD-0179 | 3PL Integration | MVP-5 | Conditional | Only if external 3PL required.
S&OP | MOD-0190 | S&OP Workflow & Sign-offs | MVP-6 | Core | Integrated plan governance/approval.
Capacity | MOD-0192 | Capacity Planning | MVP-6 | Core | Capacity/supply constraint plans.
Logistics | MOD-0183 | Shipment Tracking & POD | MVP-6 | Core | Shipment lifecycle/POD.
Logistics | MOD-0184 | Carrier Management | MVP-6 | Core | Carrier operations.
Logistics | MOD-0185 | Routing & Load Planning | MVP-6 | Core | Outbound transport planning.
Logistics | MOD-0186 | Reverse Logistics | MVP-6 | Core | Returns/reverse flow.
Logistics | MOD-0187 | Claims Management | MVP-6 | Core | Logistics claims.
Supplier Controls | MOD-0147 | Supplier Performance & Risk | MVP-6 | Supporting | Post-core supplier performance/risk.
Supplier Controls | MOD-0148 | Supplier Portal | MVP-6 | Supporting | Supplier collaboration experience.
Capability Block Governance Decisions
Decision | 6 MVPs is the recommended manufacturing-capable sequence. If distribution-only, MVP-3 BOM may be deferred and the plan collapses to 5 MVPs.
Decision | MVP-2 Procurement and MVP-3 BOM are parallel lanes after MVP-1; both converge into MVP-4.
Decision | Warehouse is not a hard prerequisite for MRP. MVP-5 can follow or overlap late MVP-4 once inventory movement contracts are stable.
Decision | MRP/replenishment proposes requirements; MOD-0141 remains SoR for requisitions and purchase orders.
Decision | Warehouse execution posts movements to MOD-0173; it never maintains a second inventory balance.
Decision | BOM/routing ownership remains MOD-0193; product/item/SKU identity remains MOD-0290.
Mandatory runtime rule | Every state-changing module must follow the Runtime Vertical-Slice rules: real persistence, server-side RBAC, tenant isolation, audit, concurrency, idempotency, controlled failure paths and no-shell UI.
Build governance | Treat this as a multi-module capability block: prepare a Delivery Capability Pack and then approved/ready-for-dev module packs before implementation.